## Matrix - Data Colection
Project Designation & Client | Project type | Project Type Qty (Uts.) | Enclosure (Y/N) | Lengh per module (m.) | Modules Qty. | PO Signature - Project Manager work start (No Wk of Year) | Year | Pre-Execution & Procurement (#ofWeeks)[Máx.28 weeks] | Execution (#ofWeeks) | Quality Check: Issues detection and remedation(#ofWeeks) | Energization (#ofWeeks) | Commissioning (#ofWeeks) | Testing type | Diassembly (#ofWeeks) | Packiging (#ofWeeks) | Shipping | Transport duration | Delivery on site | Total Project duration | Project Phase | Project Phase (Range # of Week) | Categorization | Item Affected | Vendor | Item (costs) | Root cause 1 | Estimated Cost Impact (%) | Deviation Item- Estimated Cost (€) | Carbon footprint = 10%Deviation Item- Estimated Cost (€) | Assembly Impact (days) | Assembly Impact (weeks) | Deviation Schedule - Estimated Cost (€) | Project Impact | Department Affection | Customer Affection | Categorization | Item Affected | Root cause 1 | Risk Description | Risk Cost deviation + Schedule deviation | LL Description | BP Description | How to plan it? | How to avoid/mitigate it? | Supervision / Scrum measure to take
Project MODEL 1 - ALP | Skid | 2 | 0 | 10 | 2 | 4 | 2025 | 19 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 41 | Pre-Execution & Procurement | 2 | Seismic Level | Structure |  | 35000 | Design change | 7 | 4410 | 490 | 2.3331 | 0.46662 | 314.9685 | Cost | Engineering | High | Pre-Execution & Procurement | Structure | Design change |  | 5214.9685
Project MODEL 1 - ALP | Skid | 2 | 0 | 10 | 2 | 4 | 2025 | 19 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 41 | Pre-Execution & Procurement | 2 | Design | Structure |  | 35000 | Design change | 7 | 4410 | 490 | 2.3331 | 0.46662 | 314.9685 | Cost | Engineering | High | Pre-Execution & Procurement | Structure | Design change |  | 5214.9685
Project MODEL 1 - ALP | Skid | 2 | 0 | 10 | 2 | 4 | 2025 | 19 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 41 | Pre-Execution & Procurement | 2 | Design | Structure |  | 35000 | Design change | 7 | 4410 | 490 | 2.3331 | 0.46662 | 314.9685 | Cost | Engineering | High | Pre-Execution & Procurement | Structure | Design change |  | 5214.9685
Project MODEL 1 - ALP | Skid | 2 | 0 | 10 | 2 | 4 | 2025 | 19 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 41 | Pre-Execution & Procurement | 2 | Design | Structure |  | 35000 | Design change | 7 | 4410 | 490 | 2.3331 | 0.46662 | 314.9685 | Cost | Engineering | High | Pre-Execution & Procurement | Structure | Design change |  | 5214.9685
Project MODEL 1 - ALP | Skid | 2 | 0 | 10 | 2 | 4 | 2025 | 19 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 41 | Pre-Execution & Procurement | 3 | Design | Structure |  | 35000 | Documentation error | 3 | 1890 | 210 | 0.9999 | 0.19998 | 134.9865 | Cost | Engineering | High | Pre-Execution & Procurement | Structure | Documentation error |  | 2234.9865
Project MODEL 1 - ALP | Skid | 2 | 0 | 10 | 2 | 4 | 2025 | 19 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 41 | Pre-Execution & Procurement | 4 | Change Requests | UPS |  | 54000 | Z-Other | 5 | 4860 | 540 | 1.6665 | 0.3333 | 224.9775 | Cost | Commissioning | Medium | Pre-Execution & Procurement | UPS | Z-Other |  | 5624.9775
Project MODEL 1 - ALP | Skid | 2 | 0 | 10 | 2 | 4 | 2025 | 19 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 41 | Pre-Execution & Procurement | 4 | Change Requests | Weather conditions |  | 3000 | Transport damage | 8 | 432 | 48 | 2.6664 | 0.53328 | 359.964 | Quality | Quality | Medium | Pre-Execution & Procurement | Weather conditions | Transport damage |  | 839.964
Project MODEL 1 - ALP | Skid | 2 | 0 | 10 | 2 | 4 | 2025 | 19 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 41 | Pre-Execution & Procurement | 6 | Submittal package | UPS |  | 54000 | Documentation error | 3 | 2916 | 324 | 0.9999 | 0.19998 | 134.9865 | Quality | Tendering | Low | Pre-Execution & Procurement | UPS | Documentation error |  | 3374.9865
Project MODEL 1 - ALP | Skid | 2 | 0 | 10 | 2 | 4 | 2025 | 19 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 41 | Pre-Execution & Procurement | 8 | Submittal package | Floor |  | 4500 | Documentation error | 3 | 243 | 27 | 0.9999 | 0.19998 | 134.9865 | Cost | Tendering | Low | Pre-Execution & Procurement | Floor | Documentation error |  | 404.9865
Project MODEL 1 - ALP | Skid | 2 | 0 | 10 | 2 | 4 | 2025 | 19 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 41 | Pre-Execution & Procurement | 14 | Customer & Site | Site Readiness |  |  | Communication failure | 7 | 0 | 0 | 2.3331 | 0.46662 | 314.9685 | Cost | Tendering | Medium | Pre-Execution & Procurement | Site Readiness | Communication failure |  | 314.9685
Project MODEL 1 - ALP | Skid | 2 | 0 | 10 | 2 | 4 | 2025 | 19 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 41 | Execution | 20 | Bill of Material | Busbar |  | 60000 | Inexperienced staff | 5 | 5400 | 600 | 1.6665 | 0.3333 | 224.9775 | Cost | Project Management | Medium | Execution | Busbar | Inexperienced staff |  | 6224.9775
Project MODEL 1 - ALP | Skid | 2 | 0 | 10 | 2 | 4 | 2025 | 19 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 41 | Execution | 22 | Contract | Site Energized |  |  | Lack coordination | 5 | 0 | 0 | 1.6665 | 0.3333 | 224.9775 | Schedule | Engineering | Low | Execution | Site Energized | Lack coordination |  | 224.9775
Project MODEL 1 - ALP | Skid | 2 | 0 | 10 | 2 | 4 | 2025 | 19 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 41 | Execution | 26 | Design | Main Panel A |  | 65000 | Design change | 7 | 8190 | 910 | 2.3331 | 0.46662 | 314.9685 | Cost | Tendering | Medium | Execution | Main Panel A | Design change |  | 9414.9685
Project MODEL 1 - ALP | Skid | 2 | 0 | 10 | 2 | 4 | 2025 | 19 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 41 | Execution | 26 | Design | Main Panel A |  | 65000 | Design change | 7 | 8190 | 910 | 2.3331 | 0.46662 | 314.9685 | Cost | Engineering | Low | Execution | Main Panel A | Design change |  | 9414.9685
Project MODEL 1 - ALP | Skid | 2 | 0 | 10 | 2 | 4 | 2025 | 19 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 41 | Execution | 26 | Drawings | Enclosure |  |  | Documentation error | 3 | 0 | 0 | 0.9999 | 0.19998 | 134.9865 | Schedule | Engineering | High | Execution | Enclosure | Documentation error |  | 134.9865
Project MODEL 1 - ALP | Skid | 2 | 0 | 10 | 2 | 4 | 2025 | 19 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 41 | Execution | 26 | Contract | Customer needs |  |  | Communication failure | 7 | 0 | 0 | 2.3331 | 0.46662 | 314.9685 | Schedule | Engineering | High | Execution | Customer needs | Communication failure |  | 314.9685
Project MODEL 1 - ALP | Skid | 2 | 0 | 10 | 2 | 4 | 2025 | 19 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 41 | Execution | 27 | Contract | Customer specifications |  |  | Communication failure | 7 | 0 | 0 | 2.3331 | 0.46662 | 314.9685 | Schedule | Quality | High | Execution | Customer specifications | Communication failure |  | 314.9685
Project MODEL 1 - ALP | Skid | 2 | 0 | 10 | 2 | 4 | 2025 | 19 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 41 | Execution | 27 | Resources | Z - Other |  |  | Client rejection | 10 | 0 | 0 | 3.333 | 0.6666 | 449.955 | Schedule | Production | Low | Execution | Z - Other | Client rejection |  | 449.955
Project MODEL 1 - ALP | Skid | 2 | 0 | 10 | 2 | 4 | 2025 | 19 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 41 | Execution | 28 | Manufacturing | Cable tray structs |  | 9500 | Incorrect installation | 12 | 2052 | 228 | 3.9996 | 0.79992 | 539.946 | Quality | Production | Low | Execution | Cable tray structs | Incorrect installation |  | 2819.946
Project MODEL 1 - ALP | Skid | 2 | 0 | 10 | 2 | 4 | 2025 | 19 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 41 | Execution | 28 | Manufacturing | Cable type |  |  | Incorrect installation | 12 | 0 | 0 | 3.9996 | 0.79992 | 539.946 | Quality | Production | Low | Execution | Cable type | Incorrect installation |  | 539.946
Project MODEL 1 - ALP | Skid | 2 | 0 | 10 | 2 | 4 | 2025 | 19 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 41 | Execution | 29 | Purchashing | Cable type |  |  | Needs rework | 11 | 0 | 0 | 3.6663 | 0.73326 | 494.9505 | Schedule | Production | Medium | Execution | Cable type | Needs rework |  | 494.9505
Project MODEL 1 - ALP | Skid | 2 | 0 | 10 | 2 | 4 | 2025 | 19 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 41 | Execution | 29 | Manufacturing | Main Panel A |  | 65000 | Connection error | 6 | 7020 | 780 | 1.9998 | 0.39996 | 269.973 | Cost | Production | Low | Execution | Main Panel A | Connection error |  | 8069.973
Project MODEL 1 - ALP | Skid | 2 | 0 | 10 | 2 | 4 | 2025 | 19 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 41 | Execution | 32 | Manufacturing | Main Panel B |  | 65000 | Connection error | 6 | 7020 | 780 | 1.9998 | 0.39996 | 269.973 | Cost | Production | Low | Execution | Main Panel B | Connection error |  | 8069.973
Project MODEL 1 - ALP | Skid | 2 | 0 | 10 | 2 | 4 | 2025 | 19 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 41 | Energization | 35 | Communication | Z - Other |  |  | Communication failure | 7 | 0 | 0 | 2.3331 | 0.46662 | 314.9685 | Quality | Production | Medium | Energization | Z - Other | Communication failure |  | 314.9685
Project MODEL 1 - ALP | Skid | 2 | 0 | 10 | 2 | 4 | 2025 | 19 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 41 | Commissioning | 36 | Safety | UPS |  | 54000 | Assembly error | 7 | 6804 | 756 | 2.3331 | 0.46662 | 314.9685 | Quality | Production | Medium | Commissioning | UPS | Assembly error |  | 7874.9685
Project MODEL 1 - ALP | Skid | 2 | 0 | 10 | 2 | 4 | 2025 | 19 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 41 | Commissioning | 36 | Technical Scope | UPS |  | 54000 | Factory defect | 10 | 9720 | 1080 | 3.333 | 0.6666 | 449.955 | Cost | Tendering | High | Commissioning | UPS | Factory defect |  | 11249.955
Project MODEL 1 - ALP | Skid | 2 | 0 | 10 | 2 | 4 | 2025 | 19 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 41 | Packiging | 38 | Quality | Weather conditions |  |  | Late delivery | 6 | 0 | 0 | 1.9998 | 0.39996 | 269.973 | Schedule | Quality | High | Packiging | Weather conditions | Late delivery |  | 269.973
Project MODEL 1 - ALP | Skid | 2 | 0 | 10 | 2 | 4 | 2025 | 19 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 41 | Packiging | 38 | Design | Z - Other |  |  | Assembly error | 7 | 0 | 0 | 2.3331 | 0.46662 | 314.9685 | Quality | Engineering | High | Packiging | Z - Other | Assembly error |  | 314.9685
Project MODEL 1 - ALP | Skid | 2 | 0 | 10 | 2 | 4 | 2025 | 19 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 41 | Shipping | 39 | Design | Customer needs |  |  | Missing tests | 4 | 0 | 0 | 1.3332 | 0.26664 | 179.982 | Quality | Production | High | Shipping | Customer needs | Missing tests |  | 179.982
Project MODEL 1 - ALP | Skid | 2 | 0 | 10 | 2 | 4 | 2025 | 19 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 41 | Shipping | 39 | Design | Z - Other |  |  | Late delivery | 6 | 0 | 0 | 1.9998 | 0.39996 | 269.973 | Schedule | Warehouse | Medium | Shipping | Z - Other | Late delivery |  | 269.973
Project MODEL 1 - ALP | Skid | 2 | 0 | 10 | 2 | 4 | 2025 | 19 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 41 | Shipping | 39 | Customer & Site | Site Readiness |  |  | Late delivery | 6 | 0 | 0 | 1.9998 | 0.39996 | 269.973 | Schedule | Warehouse | High | Shipping | Site Readiness | Late delivery |  | 269.973
Project MODEL 1 - ALP | Skid | 2 | 0 | 10 | 2 | 4 | 2025 | 19 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 41 | Shipping | 39 | Customer & Site | Site Energized |  |  | Schedule delay | 9 | 0 | 0 | 2.9997 | 0.59994 | 404.9595 | Schedule | Warehouse | High | Shipping | Site Energized | Schedule delay |  | 404.9595
[28 empty] | 0 | 0 | [6 empty] | 0 | 0 | 0 |  | 0
Project MODEL 2 - NDK3 | All-in-1 | 2 | 1 | 18 | 2 | 36 | 2023 | 12 | 14 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Pre-Execution & Procurement | 3 | Bill of Material | Switchboard |  | 54000 | Design change | 7 | 6804 | 756 | 2.3331 | 0.46662 | 314.9685 | Cost | Tendering | Medium | Pre-Execution & Procurement | Switchboard | Design change |  | 7874.9685
Project MODEL 2 - NDK3 | All-in-1 | 2 | 1 | 18 | 2 | 36 | 2023 | 12 | 14 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Pre-Execution & Procurement | 9 | Drawings | Cable tray structs |  | 4500 | Design change | 7 | 567 | 63 | 2.3331 | 0.46662 | 314.9685 | Cost | Tendering | High | Pre-Execution & Procurement | Cable tray structs | Design change |  | 944.9685
Project MODEL 2 - NDK3 | All-in-1 | 2 | 1 | 18 | 2 | 36 | 2023 | 12 | 14 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Pre-Execution & Procurement | 10 | Drawings | Cable tray structs |  | 4500 | Design change | 7 | 567 | 63 | 2.3331 | 0.46662 | 314.9685 | Cost | Tendering | Low | Pre-Execution & Procurement | Cable tray structs | Design change |  | 944.9685
Project MODEL 2 - NDK3 | All-in-1 | 2 | 1 | 18 | 2 | 36 | 2023 | 12 | 14 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Pre-Execution & Procurement | 10 | Submittal package | Switchboard |  | 54000 | Client rejection | 10 | 9720 | 1080 | 3.333 | 0.6666 | 449.955 | Cost | Engineering | High | Pre-Execution & Procurement | Switchboard | Client rejection |  | 11249.955
Project MODEL 2 - NDK3 | All-in-1 | 2 | 1 | 18 | 2 | 36 | 2023 | 12 | 14 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Execution | 14 | Design | Main Panel A |  | 54000 | Documentation error | 3 | 2916 | 324 | 0.9999 | 0.19998 | 134.9865 | Cost | Engineering | Low | Execution | Main Panel A | Documentation error |  | 3374.9865
Project MODEL 2 - NDK3 | All-in-1 | 2 | 1 | 18 | 2 | 36 | 2023 | 12 | 14 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Execution | 14 | Design | Main Panel A |  | 54000 | Design change | 7 | 6804 | 756 | 2.3331 | 0.46662 | 314.9685 | Schedule | Engineering | Medium | Execution | Main Panel A | Design change |  | 7874.9685
Project MODEL 2 - NDK3 | All-in-1 | 2 | 1 | 18 | 2 | 36 | 2023 | 12 | 14 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Execution | 15 | Design | Main Panel A |  | 54000 | Documentation error | 3 | 2916 | 324 | 0.9999 | 0.19998 | 134.9865 | Quality | Engineering | Medium | Execution | Main Panel A | Documentation error |  | 3374.9865
Project MODEL 2 - NDK3 | All-in-1 | 2 | 1 | 18 | 2 | 36 | 2023 | 12 | 14 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Execution | 17 | Design | Main Panel A |  | 54000 | Documentation error | 3 | 2916 | 324 | 0.9999 | 0.19998 | 134.9865 | Quality | Quality | Medium | Execution | Main Panel A | Documentation error |  | 3374.9865
Project MODEL 2 - NDK3 | All-in-1 | 2 | 1 | 18 | 2 | 36 | 2023 | 12 | 14 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Execution | 17 | Design | Cooling Inrow |  | 15500 | Ground failure | 4 | 1116 | 124 | 1.3332 | 0.26664 | 179.982 | Cost | Project Management | Low | Execution | Cooling Inrow | Ground failure |  | 1419.982
Project MODEL 2 - NDK3 | All-in-1 | 2 | 1 | 18 | 2 | 36 | 2023 | 12 | 14 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Execution | 18 | Design | Cable tray type |  | 4500 | Incorrect installation | 12 | 972 | 108 | 3.9996 | 0.79992 | 539.946 | Cost | Project Management | Low | Execution | Cable tray type | Incorrect installation |  | 1619.946
Project MODEL 2 - NDK3 | All-in-1 | 2 | 1 | 18 | 2 | 36 | 2023 | 12 | 14 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Execution | 21 | Design | Doors |  | 39500 | Schedule delay | 9 | 6399 | 711 | 2.9997 | 0.59994 | 404.9595 | Schedule | Project Management | Low | Execution | Doors | Schedule delay |  | 7514.9595
Project MODEL 2 - NDK3 | All-in-1 | 2 | 1 | 18 | 2 | 36 | 2023 | 12 | 14 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Execution | 22 | Purchashing | Doors |  | 39500 | Schedule delay | 9 | 6399 | 711 | 2.9997 | 0.59994 | 404.9595 | Schedule | Project Management | Low | Execution | Doors | Schedule delay |  | 7514.9595
Project MODEL 2 - NDK3 | All-in-1 | 2 | 1 | 18 | 2 | 36 | 2023 | 12 | 14 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Execution | 25 | Technical Scope | Vertical support |  | 3000 | Incorrect installation | 12 | 648 | 72 | 3.9996 | 0.79992 | 539.946 | Quality | Quality | Medium | Execution | Vertical support | Incorrect installation |  | 1259.946
Project MODEL 2 - NDK3 | All-in-1 | 2 | 1 | 18 | 2 | 36 | 2023 | 12 | 14 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Energization | 29 | Communication | UPS |  | 60500 | No validation | 5 | 5445 | 605 | 1.6665 | 0.3333 | 224.9775 | Quality | Project Management | Low | Energization | UPS | No validation |  | 6274.9775
Project MODEL 2 - NDK3 | All-in-1 | 2 | 1 | 18 | 2 | 36 | 2023 | 12 | 14 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Packiging | 32 | Safety | Z - Other |  |  | Safety error | 6 | 0 | 0 | 1.9998 | 0.39996 | 269.973 | Quality | Warehouse | High | Packiging | Z - Other | Safety error |  | 269.973
Project MODEL 2 - NDK3 | All-in-1 | 2 | 1 | 18 | 2 | 36 | 2023 | 12 | 14 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Shipping | 33 | Transport/Logistics | Z - Other |  |  | Schedule delay | 9 | 0 | 0 | 2.9997 | 0.59994 | 404.9595 | Schedule | Project Management | High | Shipping | Z - Other | Schedule delay |  | 404.9595
[28 empty] | 0 | 0 | [5 empty] | Low |  |  |  |  | 0
Project MODEL 3 - NND4 | All-in-1 | 2 | 1 | 18 | 2 | 28 | 2024 | 10 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 31 | Pre-Execution & Procurement | 4 | Design | Cable grand |  | 2000 | Design change | 7 | 252 | 28 | 2.3331 | 0.46662 | 314.9685 | Cost | Tendering | Low | Pre-Execution & Procurement | Cable grand | Design change |  | 594.9685
Project MODEL 3 - NND4 | All-in-1 | 2 | 1 | 18 | 2 | 28 | 2024 | 10 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 31 | Pre-Execution & Procurement | 4 | KOM Client | Customer needs |  |  | Client rejection | 10 | 0 | 0 | 3.333 | 0.6666 | 449.955 | Cost | Project Management | Low | Pre-Execution & Procurement | Customer needs | Client rejection |  | 449.955
Project MODEL 3 - NND4 | All-in-1 | 2 | 1 | 18 | 2 | 28 | 2024 | 10 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 31 | Pre-Execution & Procurement | 4 | KOM Factory | Customer specifications |  |  | Lack coordination | 5 | 0 | 0 | 1.6665 | 0.3333 | 224.9775 | Cost | Project Management | Medium | Pre-Execution & Procurement | Customer specifications | Lack coordination |  | 224.9775
Project MODEL 3 - NND4 | All-in-1 | 2 | 1 | 18 | 2 | 28 | 2024 | 10 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 31 | Pre-Execution & Procurement | 4 | Submittal package | Customer specifications |  |  | Design change | 7 | 0 | 0 | 2.3331 | 0.46662 | 314.9685 | Scope | Tendering | High | Pre-Execution & Procurement | Customer specifications | Design change |  | 314.9685
Project MODEL 3 - NND4 | All-in-1 | 2 | 1 | 18 | 2 | 28 | 2024 | 10 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 31 | Pre-Execution & Procurement | 4 | Technical Scope | Customer specifications |  |  | Design change | 7 | 0 | 0 | 2.3331 | 0.46662 | 314.9685 | Sales | Tendering | Low | Pre-Execution & Procurement | Customer specifications | Design change |  | 314.9685
Project MODEL 3 - NND4 | All-in-1 | 2 | 1 | 18 | 2 | 28 | 2024 | 10 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 31 | Pre-Execution & Procurement | 5 | Design | Cable tray type |  | 3500 | Design change | 7 | 441 | 49 | 2.3331 | 0.46662 | 314.9685 | Quality | Engineering | Low | Pre-Execution & Procurement | Cable tray type | Design change |  | 804.9685
Project MODEL 3 - NND4 | All-in-1 | 2 | 1 | 18 | 2 | 28 | 2024 | 10 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 31 | Pre-Execution & Procurement | 6 | Design | Doors |  | 41000 | Incorrect wiring | 9 | 6642 | 738 | 2.9997 | 0.59994 | 404.9595 | Schedule | Engineering | Medium | Pre-Execution & Procurement | Doors | Incorrect wiring |  | 7784.9595
Project MODEL 3 - NND4 | All-in-1 | 2 | 1 | 18 | 2 | 28 | 2024 | 10 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 31 | Pre-Execution & Procurement | 6 | Design | Enclosure |  | 21500 | Wrong drawings | 4 | 1548 | 172 | 1.3332 | 0.26664 | 179.982 | Cost | Engineering | Medium | Pre-Execution & Procurement | Enclosure | Wrong drawings |  | 1899.982
Project MODEL 3 - NND4 | All-in-1 | 2 | 1 | 18 | 2 | 28 | 2024 | 10 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 31 | Pre-Execution & Procurement | 7 | Design | Main Panel A |  | 56000 | Design change | 7 | 7056 | 784 | 2.3331 | 0.46662 | 314.9685 | Quality | Engineering | Low | Pre-Execution & Procurement | Main Panel A | Design change |  | 8154.9685
Project MODEL 3 - NND4 | All-in-1 | 2 | 1 | 18 | 2 | 28 | 2024 | 10 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 31 | Pre-Execution & Procurement | 7 | Design | Main Panel B |  | 59000 | Design change | 7 | 7434 | 826 | 2.3331 | 0.46662 | 314.9685 | Cost | Engineering | Low | Pre-Execution & Procurement | Main Panel B | Design change |  | 8574.9685
Project MODEL 3 - NND4 | All-in-1 | 2 | 1 | 18 | 2 | 28 | 2024 | 10 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 31 | Pre-Execution & Procurement | 7 | Design | PDU |  | 8000 | Design change | 7 | 1008 | 112 | 2.3331 | 0.46662 | 314.9685 | Quality | Engineering | Low | Pre-Execution & Procurement | PDU | Design change |  | 1434.9685
Project MODEL 3 - NND4 | All-in-1 | 2 | 1 | 18 | 2 | 28 | 2024 | 10 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 31 | Pre-Execution & Procurement | 10 | Design | Vertical support |  | 3000 | Design change | 7 | 378 | 42 | 2.3331 | 0.46662 | 314.9685 | Quality | Project Management | Low | Pre-Execution & Procurement | Vertical support | Design change |  | 734.9685
Project MODEL 3 - NND4 | All-in-1 | 2 | 1 | 18 | 2 | 28 | 2024 | 10 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 31 | Execution | 12 | Change Requests | PDU |  | 8000 | Design change | 7 | 1008 | 112 | 2.3331 | 0.46662 | 314.9685 | Quality | Project Management | High | Execution | PDU | Design change |  | 1434.9685
Project MODEL 3 - NND4 | All-in-1 | 2 | 1 | 18 | 2 | 28 | 2024 | 10 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 31 | Execution | 15 | Design | Cable grand |  | 2500 | Factory defect | 10 | 450 | 50 | 3.333 | 0.6666 | 449.955 | Quality | Project Management | Medium | Execution | Cable grand | Factory defect |  | 949.955
Project MODEL 3 - NND4 | All-in-1 | 2 | 1 | 18 | 2 | 28 | 2024 | 10 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 31 | Execution | 15 | Drawings | Cable grand |  | 2000 | Design change | 7 | 252 | 28 | 2.3331 | 0.46662 | 314.9685 | Cost | Project Management | Low | Execution | Cable grand | Design change |  | 594.9685
Project MODEL 3 - NND4 | All-in-1 | 2 | 1 | 18 | 2 | 28 | 2024 | 10 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 31 | Execution | 15 | Drawings | Vertical support |  | 3000 | Documentation error | 3 | 162 | 18 | 0.9999 | 0.19998 | 134.9865 | Schedule | Project Management | Medium | Execution | Vertical support | Documentation error |  | 314.9865
Project MODEL 3 - NND4 | All-in-1 | 2 | 1 | 18 | 2 | 28 | 2024 | 10 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 31 | Execution | 16 | Technical Scope | Switchboard |  | 53500 | Connectivity failure | 7 | 6741 | 749 | 2.3331 | 0.46662 | 314.9685 | Cost | Project Management | Low | Execution | Switchboard | Connectivity failure |  | 7804.9685
Project MODEL 3 - NND4 | All-in-1 | 2 | 1 | 18 | 2 | 28 | 2024 | 10 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 31 | Execution | 17 | Submittal package | Switchboard |  | 53500 | Design change | 7 | 6741 | 749 | 2.3331 | 0.46662 | 314.9685 | Cost | Engineering | High | Execution | Switchboard | Design change |  | 7804.9685
Project MODEL 3 - NND4 | All-in-1 | 2 | 1 | 18 | 2 | 28 | 2024 | 10 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 31 | Execution | 19 | Resources | Cooling Inrow |  | 14000 | Inexperienced staff | 5 | 1260 | 140 | 1.6665 | 0.3333 | 224.9775 | Quality | Project Management | Medium | Execution | Cooling Inrow | Inexperienced staff |  | 1624.9775
Project MODEL 3 - NND4 | All-in-1 | 2 | 1 | 18 | 2 | 28 | 2024 | 10 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 31 | Execution | 19 | Technical Scope | Cooling Inrow |  | 14000 | Missing kit | 5 | 1260 | 140 | 1.6665 | 0.3333 | 224.9775 | Cost | Project Management | Low | Execution | Cooling Inrow | Missing kit |  | 1624.9775
Project MODEL 3 - NND4 | All-in-1 | 2 | 1 | 18 | 2 | 28 | 2024 | 10 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 31 | Execution | 20 | Quality | Labels |  | 3500 | Labeling error | 3 | 189 | 21 | 0.9999 | 0.19998 | 134.9865 | Schedule | Project Management | Low | Execution | Labels | Labeling error |  | 344.9865
Project MODEL 3 - NND4 | All-in-1 | 2 | 1 | 18 | 2 | 28 | 2024 | 10 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 31 | Execution | 21 | Commissioning & Testing | Main Panel A |  | 56000 | Configuration error | 6 | 6048 | 672 | 1.9998 | 0.39996 | 269.973 | Schedule | Commissioning | Low | Execution | Main Panel A | Configuration error |  | 6989.973
Project MODEL 3 - NND4 | All-in-1 | 2 | 1 | 18 | 2 | 28 | 2024 | 10 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 31 | Energization | 25 | Commissioning & Testing | Main Panel B |  | 65500 | Configuration error | 6 | 7074 | 786 | 1.9998 | 0.39996 | 269.973 | Schedule | Commissioning | Low | Energization | Main Panel B | Configuration error |  | 8129.973
Project MODEL 3 - NND4 | All-in-1 | 2 | 1 | 18 | 2 | 28 | 2024 | 10 | 12 | 2 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 31 | Shipping | 29 | Transport/Logistics | Weather conditions |  |  | Transport damage | 8 | 0 | 0 | 2.6664 | 0.53328 | 359.964 | Cost | Warehouse | Medium | Shipping | Weather conditions | Transport damage |  | 359.964
[28 empty] | 0 | 0 | [10 empty] | 0
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 5 | Drawings | Structure |  | 33500 | Design change | 7 | 10552.5 | 1172.5 | 2.3331 | 0.46662 | 314.9685 | Quality | Tendering | High | Pre-Execution & Procurement | Structure | Design change |  | 12039.9685
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 5 | Design | Structure |  | 36500 | Wrong drawings | 4 | 6570 | 730 | 1.3332 | 0.26664 | 179.982 | Cost | Engineering | High | Pre-Execution & Procurement | Structure | Wrong drawings |  | 7479.982
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 5 | Drawings | Structure |  | 36500 | Measurement error | 4 | 6570 | 730 | 1.3332 | 0.26664 | 179.982 | Cost | Engineering | Medium | Pre-Execution & Procurement | Structure | Measurement error |  | 7479.982
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 5 | Change Requests | Main Panel A |  | 55000 | Labeling error | 3 | 7425 | 825 | 0.9999 | 0.19998 | 134.9865 | Cost | Tendering | Low | Pre-Execution & Procurement | Main Panel A | Labeling error |  | 8384.9865
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 7 | Change Requests | Main Panel A |  | 55000 | Wrong documentation | 3 | 7425 | 825 | 0.9999 | 0.19998 | 134.9865 | Quality | Tendering | Medium | Pre-Execution & Procurement | Main Panel A | Wrong documentation |  | 8384.9865
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 8 | Submittal package | Customer specifications |  |  | Z-Other | 5 | 0 | 0 | 1.6665 | 0.3333 | 224.9775 | Quality | Engineering | High | Pre-Execution & Procurement | Customer specifications | Z-Other |  | 224.9775
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 10 | Quality | Cable tray structs |  | 20000 | Alignment error | 5 | 4500 | 500 | 1.6665 | 0.3333 | 224.9775 | Quality | Quality | Low | Pre-Execution & Procurement | Cable tray structs | Alignment error |  | 5224.9775
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 12 | Submittal package | Customer specifications |  | 1500 | Z-Other | 5 | 337.5 | 37.5 | 1.6665 | 0.3333 | 224.9775 | Cost | Engineering | Low | Pre-Execution & Procurement | Customer specifications | Z-Other |  | 599.9775
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 12 | Change Requests | Cable type |  | 42500 | Wrong material | 6 | 11475 | 1275 | 1.9998 | 0.39996 | 269.973 | Cost | Tendering | Medium | Pre-Execution & Procurement | Cable type | Wrong material |  | 13019.973
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 13 | Change Requests | Doors |  | 11000 | Design change | 7 | 3465 | 385 | 2.3331 | 0.46662 | 314.9685 | Cost | Tendering | Low | Pre-Execution & Procurement | Doors | Design change |  | 4164.9685
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 13 | Change Requests | Floor Termination |  | 49500 | Design change | 7 | 15592.5 | 1732.5 | 2.3331 | 0.46662 | 314.9685 | Quality | Tendering | High | Pre-Execution & Procurement | Floor Termination | Design change |  | 17639.9685
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 14 | Drawings | Busbar |  | 35000 | Design change | 7 | 11025 | 1225 | 2.3331 | 0.46662 | 314.9685 | Quality | Engineering | Low | Pre-Execution & Procurement | Busbar | Design change |  | 12564.9685
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 14 | Change Requests | Main Panel A |  | 55000 | Design change | 7 | 17325 | 1925 | 2.3331 | 0.46662 | 314.9685 | Cost | Engineering | High | Pre-Execution & Procurement | Main Panel A | Design change |  | 19564.9685
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 14 | Change Requests | Main Panel A |  | 55000 | Design change | 7 | 17325 | 1925 | 2.3331 | 0.46662 | 314.9685 | Quality | Engineering | High | Pre-Execution & Procurement | Main Panel A | Design change |  | 19564.9685
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 14 | Change Requests | Main Panel A |  | 55000 | Design change | 7 | 17325 | 1925 | 2.3331 | 0.46662 | 314.9685 | Cost | Engineering | Low | Pre-Execution & Procurement | Main Panel A | Design change |  | 19564.9685
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 14 | Technical Scope | Z - Other |  |  | Z-Other | 5 | 0 | 0 | 1.6665 | 0.3333 | 224.9775 | Scope | Engineering | Low | Pre-Execution & Procurement | Z - Other | Z-Other |  | 224.9775
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 14 | Change Requests | Battery Cabinet/Rack |  | 88000 | Wrong drawings | 4 | 15840 | 1760 | 1.3332 | 0.26664 | 179.982 | Cost | Engineering | Medium | Pre-Execution & Procurement | Battery Cabinet/Rack | Wrong drawings |  | 17779.982
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 14 | Change Requests | Cable grand |  | 21500 | Design change | 7 | 6772.5 | 752.5 | 2.3331 | 0.46662 | 314.9685 | Cost | Quality | Low | Pre-Execution & Procurement | Cable grand | Design change |  | 7839.9685
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 14 | Change Requests | Cable tray structs |  | 20000 | Design change | 7 | 6300 | 700 | 2.3331 | 0.46662 | 314.9685 | Quality | Project Management | Low | Pre-Execution & Procurement | Cable tray structs | Design change |  | 7314.9685
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 15 | Seismic Level | Customer needs |  |  | Design change | 7 | 0 | 0 | 2.3331 | 0.46662 | 314.9685 | Cost | Tendering | Low | Pre-Execution & Procurement | Customer needs | Design change |  | 314.9685
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 15 | Change Requests | Cable tray type |  | 20000 | Design change | 7 | 6300 | 700 | 2.3331 | 0.46662 | 314.9685 | Quality | Engineering | Low | Pre-Execution & Procurement | Cable tray type | Design change |  | 7314.9685
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 15 | Technical Scope | Customer needs |  |  | Design change | 7 | 0 | 0 | 2.3331 | 0.46662 | 314.9685 | Sales | Engineering | Low | Pre-Execution & Procurement | Customer needs | Design change |  | 314.9685
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 15 | Technical Scope | Customer specifications |  |  | Design change | 7 | 0 | 0 | 2.3331 | 0.46662 | 314.9685 | Scope | Tendering | Low | Pre-Execution & Procurement | Customer specifications | Design change |  | 314.9685
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 15 | Change Requests | Main Panel A |  | 55000 | Design change | 7 | 17325 | 1925 | 2.3331 | 0.46662 | 314.9685 | Cost | Tendering | High | Pre-Execution & Procurement | Main Panel A | Design change |  | 19564.9685
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 15 | Change Requests | Main Panel A |  | 55000 | Design change | 7 | 17325 | 1925 | 2.3331 | 0.46662 | 314.9685 | Cost | Project Management | High | Pre-Execution & Procurement | Main Panel A | Design change |  | 19564.9685
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 15 | Change Requests | Main Panel A |  | 55000 | Design change | 7 | 17325 | 1925 | 2.3331 | 0.46662 | 314.9685 | Cost | Project Management | Low | Pre-Execution & Procurement | Main Panel A | Design change |  | 19564.9685
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 15 | Change Requests | Main Panel A |  | 55000 | Design change | 7 | 17325 | 1925 | 2.3331 | 0.46662 | 314.9685 | Cost | Engineering | Low | Pre-Execution & Procurement | Main Panel A | Design change |  | 19564.9685
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 15 | Customer & Site | Site Readiness |  |  | Inexperienced staff | 5 | 0 | 0 | 1.6665 | 0.3333 | 224.9775 | Schedule | Engineering | Medium | Pre-Execution & Procurement | Site Readiness | Inexperienced staff |  | 224.9775
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 16 | Purchashing | Busbar |  | 35000 | Lack coordination | 5 | 7875 | 875 | 1.6665 | 0.3333 | 224.9775 | Schedule | Project Management | Low | Pre-Execution & Procurement | Busbar | Lack coordination |  | 8974.9775
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 16 | Contract | Site Readiness |  |  | Z-Other | 5 | 0 | 0 | 1.6665 | 0.3333 | 224.9775 | Cost | Tendering | Low | Pre-Execution & Procurement | Site Readiness | Z-Other |  | 224.9775
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 16 | Purchashing | Battery LiThium |  | 102500 | Schedule delay | 9 | 41512.5 | 4612.5 | 2.9997 | 0.59994 | 404.9595 | Schedule | Engineering | High | Pre-Execution & Procurement | Battery LiThium | Schedule delay |  | 46529.9595
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 16 | Change Requests | Monitoring Panel |  | 61500 | Measurement error | 4 | 11070 | 1230 | 1.3332 | 0.26664 | 179.982 | Quality | Project Management | Medium | Pre-Execution & Procurement | Monitoring Panel | Measurement error |  | 12479.982
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 16 | Customer & Site | Site Energized |  |  | Lack coordination | 5 | 0 | 0 | 1.6665 | 0.3333 | 224.9775 | Schedule | Project Management | Medium | Pre-Execution & Procurement | Site Energized | Lack coordination |  | 224.9775
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 16 | Change Requests | Busbar |  | 35000 | Factory defect | 10 | 15750 | 1750 | 3.333 | 0.6666 | 449.955 | Quality | Engineering | Medium | Pre-Execution & Procurement | Busbar | Factory defect |  | 17949.955
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 16 | Change Requests | Requiring site works |  | 24500 | Needs rework | 11 | 12127.5 | 1347.5 | 3.6663 | 0.73326 | 494.9505 | Quality | Engineering | Low | Pre-Execution & Procurement | Requiring site works | Needs rework |  | 13969.9505
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 16 | Communication | Z - Other |  |  | Inexperienced staff | 5 | 0 | 0 | 1.6665 | 0.3333 | 224.9775 | Quality | Project Management | Medium | Pre-Execution & Procurement | Z - Other | Inexperienced staff |  | 224.9775
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 16 | Communication | Z - Other |  |  | Language error | 3 | 0 | 0 | 0.9999 | 0.19998 | 134.9865 | Quality | Project Management | Low | Pre-Execution & Procurement | Z - Other | Language error |  | 134.9865
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 16 | Contract | Supply Chain |  |  | Client rejection | 10 | 0 | 0 | 3.333 | 0.6666 | 449.955 | Scope | Project Management | Low | Pre-Execution & Procurement | Supply Chain | Client rejection |  | 449.955
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 17 | Submittal package | Z - Other |  |  | Client rejection | 10 | 0 | 0 | 3.333 | 0.6666 | 449.955 | Scope | Project Management | Low | Pre-Execution & Procurement | Z - Other | Client rejection |  | 449.955
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 18 | Communication | Z - Other |  |  | Missing training | 4 | 0 | 0 | 1.3332 | 0.26664 | 179.982 | Cost | Project Management | Medium | Pre-Execution & Procurement | Z - Other | Missing training |  | 179.982
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 18 | Change Requests | Customer specifications |  | 120500 | Missing tests | 4 | 21690 | 2410 | 1.3332 | 0.26664 | 179.982 | Cost | Tendering | Medium | Pre-Execution & Procurement | Customer specifications | Missing tests |  | 24279.982
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 18 | Change Requests | Doors |  | 11000 | Design change | 7 | 3465 | 385 | 2.3331 | 0.46662 | 314.9685 | Cost | Engineering | Low | Pre-Execution & Procurement | Doors | Design change |  | 4164.9685
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 18 | Change Requests | Cable tray structs |  | 20000 | Design change | 7 | 6300 | 700 | 2.3331 | 0.46662 | 314.9685 | Cost | Engineering | Low | Pre-Execution & Procurement | Cable tray structs | Design change |  | 7314.9685
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 18 | Change Requests | Main Panel A |  | 55000 | Documentation error | 3 | 7425 | 825 | 0.9999 | 0.19998 | 134.9865 | Cost | Engineering | Medium | Pre-Execution & Procurement | Main Panel A | Documentation error |  | 8384.9865
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 19 | Change Requests | Main Panel A |  | 55000 | Design change | 7 | 17325 | 1925 | 2.3331 | 0.46662 | 314.9685 | Cost | Engineering | Medium | Pre-Execution & Procurement | Main Panel A | Design change |  | 19564.9685
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 20 | Communication | Customer needs |  |  | Inexperienced staff | 5 | 0 | 0 | 1.6665 | 0.3333 | 224.9775 | Quality | Engineering | Low | Pre-Execution & Procurement | Customer needs | Inexperienced staff |  | 224.9775
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 21 | Change Requests | Main Panel A |  | 55000 | Design change | 7 | 17325 | 1925 | 2.3331 | 0.46662 | 314.9685 | Quality | Engineering | Low | Pre-Execution & Procurement | Main Panel A | Design change |  | 19564.9685
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 22 | Commissioning & Testing | Netbots |  | 48500 | Communication failure | 7 | 15277.5 | 1697.5 | 2.3331 | 0.46662 | 314.9685 | Cost | Engineering | Low | Pre-Execution & Procurement | Netbots | Communication failure |  | 17289.9685
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 23 | Transport/Logistics | Customer needs |  | 170500 | Lack coordination | 5 | 38362.5 | 4262.5 | 1.6665 | 0.3333 | 224.9775 | Schedule | Warehouse | Medium | Pre-Execution & Procurement | Customer needs | Lack coordination |  | 42849.9775
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 23 | Change Requests | Cable grand |  | 21500 | Incorrect wiring | 9 | 8707.5 | 967.5 | 2.9997 | 0.59994 | 404.9595 | Quality | Project Management | Medium | Pre-Execution & Procurement | Cable grand | Incorrect wiring |  | 10079.9595
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 23 | Resources | Z - Other |  |  | Inexperienced staff | 5 | 0 | 0 | 1.6665 | 0.3333 | 224.9775 | Quality | Engineering | Medium | Pre-Execution & Procurement | Z - Other | Inexperienced staff |  | 224.9775
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 23 | Communication | Z - Other |  |  | Z-Other | 5 | 0 | 0 | 1.6665 | 0.3333 | 224.9775 | Quality | Project Management | Low | Pre-Execution & Procurement | Z - Other | Z-Other |  | 224.9775
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 24 | Change Requests | Cooling CRAH |  | 148500 | Alignment error | 5 | 33412.5 | 3712.5 | 1.6665 | 0.3333 | 224.9775 | Cost | Engineering | Low | Pre-Execution & Procurement | Cooling CRAH | Alignment error |  | 37349.9775
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 24 | Change Requests | Cooling CRAH |  | 148500 | Sensor failure | 5 | 33412.5 | 3712.5 | 1.6665 | 0.3333 | 224.9775 | Cost | Engineering | Low | Pre-Execution & Procurement | Cooling CRAH | Sensor failure |  | 37349.9775
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 24 | Change Requests | Labels |  |  | Language error | 3 | 0 | 0 | 0.9999 | 0.19998 | 134.9865 | Quality | Engineering | Low | Pre-Execution & Procurement | Labels | Language error |  | 134.9865
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Pre-Execution & Procurement | 27 | Manufacturing | Z - Other |  |  | No supervision | 6 | 0 | 0 | 1.9998 | 0.39996 | 269.973 | Quality | Engineering | Medium | Pre-Execution & Procurement | Z - Other | No supervision |  | 269.973
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Execution | 28 | Quality | Z - Other |  |  | No calibration | 4 | 0 | 0 | 1.3332 | 0.26664 | 179.982 | Quality | Project Management | Medium | Execution | Z - Other | No calibration |  | 179.982
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Execution | 28 | Resources | Z - Other |  |  | Lack coordination | 5 | 0 | 0 | 1.6665 | 0.3333 | 224.9775 | Schedule | Project Management | Low | Execution | Z - Other | Lack coordination |  | 224.9775
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Execution | 29 | Quality | Z - Other |  |  | Ground failure | 4 | 0 | 0 | 1.3332 | 0.26664 | 179.982 | Quality | Project Management | Low | Execution | Z - Other | Ground failure |  | 179.982
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Execution | 32 | Drawings | Structure |  | 33500 | Design change | 7 | 10552.5 | 1172.5 | 2.3331 | 0.46662 | 314.9685 | Cost | Engineering | Low | Execution | Structure | Design change |  | 12039.9685
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Execution | 33 | Contract | Supply Chain |  |  | Client rejection | 10 | 0 | 0 | 3.333 | 0.6666 | 449.955 | Cost | Project Management | Low | Execution | Supply Chain | Client rejection |  | 449.955
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Execution | 34 | Resources | Z - Other |  |  | Inexperienced staff | 5 | 0 | 0 | 1.6665 | 0.3333 | 224.9775 | Quality | Project Management | Medium | Execution | Z - Other | Inexperienced staff |  | 224.9775
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Execution | 35 | Manufacturing | Z - Other |  |  | No supervision | 6 | 0 | 0 | 1.9998 | 0.39996 | 269.973 | Quality | Project Management | Low | Execution | Z - Other | No supervision |  | 269.973
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Execution | 35 | Drawings | Customer needs |  |  | Design change | 7 | 0 | 0 | 2.3331 | 0.46662 | 314.9685 | Scope | Project Management | Low | Execution | Customer needs | Design change |  | 314.9685
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Execution | 38 | Resources | Z - Other |  |  | Inexperienced staff | 5 | 0 | 0 | 1.6665 | 0.3333 | 224.9775 | Schedule | Project Management | High | Execution | Z - Other | Inexperienced staff |  | 224.9775
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Execution | 43 | Manufacturing | Cable tray structs |  | 20000 | Assembly error | 7 | 6300 | 700 | 2.3331 | 0.46662 | 314.9685 | Schedule | Project Management | Low | Execution | Cable tray structs | Assembly error |  | 7314.9685
Project MODEL 4 - COMPASS PH1 | Power Module (PM) | 5 | 1 | 18 | 5 | 31 | 2022 | 28 | 19 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 66 | Execution | 47 | Manufacturing | Busbar |  | 35000 | Assembly error | 7 | 11025 | 1225 | 2.3331 | 0.46662 | 314.9685 | Schedule | Project Management | Low | Execution | Busbar | Assembly error |  | 12564.9685
[28 empty] | 0 | 0 | [10 empty] | 0
Project MODEL 5 - COMPASS PH2 | Power Module (PM) | 5 | 1 | 18 | 5 | 49 | 2022 | 20 | 17 | 2 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 55 | Execution | 21 | Drawings | Structure |  | 33500 | Design change | 7 | 10552.5 | 1172.5 | 2.3331 | 0.46662 | 314.9685 | Cost | Engineering | Low | Execution | Structure | Design change |  | 12039.9685
Project MODEL 5 - COMPASS PH2 | Power Module (PM) | 5 | 1 | 18 | 5 | 49 | 2022 | 20 | 17 | 2 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 55 | Execution | 22 | Change Requests | Requiring site works |  | 24500 | Needs rework | 11 | 12127.5 | 1347.5 | 3.6663 | 0.73326 | 494.9505 | Cost | Project Management | High | Execution | Requiring site works | Needs rework |  | 13969.9505
Project MODEL 5 - COMPASS PH2 | Power Module (PM) | 5 | 1 | 18 | 5 | 49 | 2022 | 20 | 17 | 2 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 55 | Execution | 22 | Change Requests | Customer specifications |  | 120500 | Missing tests | 4 | 21690 | 2410 | 1.3332 | 0.26664 | 179.982 | Cost | Engineering | High | Execution | Customer specifications | Missing tests |  | 24279.982
Project MODEL 5 - COMPASS PH2 | Power Module (PM) | 5 | 1 | 18 | 5 | 49 | 2022 | 20 | 17 | 2 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 55 | Execution | 22 | Contract | Supply Chain |  |  | Client rejection | 10 | 0 | 0 | 3.333 | 0.6666 | 449.955 | Cost | Project Management | Low | Execution | Supply Chain | Client rejection |  | 449.955
Project MODEL 5 - COMPASS PH2 | Power Module (PM) | 5 | 1 | 18 | 5 | 49 | 2022 | 20 | 17 | 2 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 55 | Execution | 25 | Resources | Z - Other |  |  | Inexperienced staff | 5 | 0 | 0 | 1.6665 | 0.3333 | 224.9775 | Quality | Project Management | Medium | Execution | Z - Other | Inexperienced staff |  | 224.9775
Project MODEL 5 - COMPASS PH2 | Power Module (PM) | 5 | 1 | 18 | 5 | 49 | 2022 | 20 | 17 | 2 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 55 | Execution | 25 | Manufacturing | Z - Other |  |  | No supervision | 6 | 0 | 0 | 1.9998 | 0.39996 | 269.973 | Quality | Project Management | Low | Execution | Z - Other | No supervision |  | 269.973
Project MODEL 5 - COMPASS PH2 | Power Module (PM) | 5 | 1 | 18 | 5 | 49 | 2022 | 20 | 17 | 2 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 55 | Execution | 26 | Drawings | Customer needs |  |  | Design change | 7 | 0 | 0 | 2.3331 | 0.46662 | 314.9685 | Scope | Project Management | Low | Execution | Customer needs | Design change |  | 314.9685
Project MODEL 5 - COMPASS PH2 | Power Module (PM) | 5 | 1 | 18 | 5 | 49 | 2022 | 20 | 17 | 2 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 55 | Execution | 31 | Resources | Z - Other |  |  | Inexperienced staff | 5 | 0 | 0 | 1.6665 | 0.3333 | 224.9775 | Schedule | Project Management | Medium | Execution | Z - Other | Inexperienced staff |  | 224.9775
Project MODEL 5 - COMPASS PH2 | Power Module (PM) | 5 | 1 | 18 | 5 | 49 | 2022 | 20 | 17 | 2 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 55 | Execution | 31 | Manufacturing | Cable tray structs |  | 20000 | Assembly error | 7 | 6300 | 700 | 2.3331 | 0.46662 | 314.9685 | Schedule | Project Management | Low | Execution | Cable tray structs | Assembly error |  | 7314.9685
Project MODEL 5 - COMPASS PH2 | Power Module (PM) | 5 | 1 | 18 | 5 | 49 | 2022 | 20 | 17 | 2 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 55 | Execution | 36 | Manufacturing | Busbar |  | 35000 | Assembly error | 7 | 11025 | 1225 | 2.3331 | 0.46662 | 314.9685 | Schedule | Project Management | Low | Execution | Busbar | Assembly error |  | 12564.9685
[28 empty] | 0 | 0 | [10 empty] | 0
Project MODEL 6 - COMPASS PH3 | Power Module (PM) | 5 | 1 | 18 | 5 | 14 | 2023 | 17 | 16 | 2 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 51 | Execution | 5 | Contract | Supply Chain |  |  | Client rejection | 10 | 0 | 0 | 3.333 | 0.6666 | 449.955 | Quality | Tendering | Low | Execution | Supply Chain | Client rejection |  | 449.955
Project MODEL 6 - COMPASS PH3 | Power Module (PM) | 5 | 1 | 18 | 5 | 14 | 2023 | 17 | 16 | 2 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 51 | Execution | 5 | Drawings | Main Panel A |  | 55000 | Design change | 7 | 17325 | 1925 | 2.3331 | 0.46662 | 314.9685 | Cost | Production | Low | Execution | Main Panel A | Design change |  | 19564.9685
Project MODEL 6 - COMPASS PH3 | Power Module (PM) | 5 | 1 | 18 | 5 | 14 | 2023 | 17 | 16 | 2 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 51 | Execution | 7 | Communication | Customer needs |  |  | Missing support | 4 | 0 | 0 | 1.3332 | 0.26664 | 179.982 | Scope | Project Management | Low | Execution | Customer needs | Missing support |  | 179.982
Project MODEL 6 - COMPASS PH3 | Power Module (PM) | 5 | 1 | 18 | 5 | 14 | 2023 | 17 | 16 | 2 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 51 | Execution | 8 | Change Requests | Requiring site works |  | 24500 | Needs rework | 11 | 12127.5 | 1347.5 | 3.6663 | 0.73326 | 494.9505 | Sales | Tendering | High | Execution | Requiring site works | Needs rework |  | 13969.9505
Project MODEL 6 - COMPASS PH3 | Power Module (PM) | 5 | 1 | 18 | 5 | 14 | 2023 | 17 | 16 | 2 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 51 | Execution | 8 | Drawings | Busbar |  | 35000 | Documentation error | 3 | 4725 | 525 | 0.9999 | 0.19998 | 134.9865 | Cost | Engineering | Medium | Execution | Busbar | Documentation error |  | 5384.9865
Project MODEL 6 - COMPASS PH3 | Power Module (PM) | 5 | 1 | 18 | 5 | 14 | 2023 | 17 | 16 | 2 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 51 | Execution | 19 | Change Requests | Customer specifications |  | 120500 | Missing tests | 4 | 21690 | 2410 | 1.3332 | 0.26664 | 179.982 | Cost | Project Management | High | Execution | Customer specifications | Missing tests |  | 24279.982
Project MODEL 6 - COMPASS PH3 | Power Module (PM) | 5 | 1 | 18 | 5 | 14 | 2023 | 17 | 16 | 2 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 51 | Execution | 21 | Manufacturing | Panelling |  | 62000 | No spares | 3 | 8370 | 930 | 0.9999 | 0.19998 | 134.9865 | Cost | Engineering | Low | Execution | Panelling | No spares |  | 9434.9865
Project MODEL 6 - COMPASS PH3 | Power Module (PM) | 5 | 1 | 18 | 5 | 14 | 2023 | 17 | 16 | 2 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 51 | Execution | 25 | Manufacturing | Enclosure |  | 30500 | Factory defect | 10 | 13725 | 1525 | 3.333 | 0.6666 | 449.955 | Quality | Engineering | Low | Execution | Enclosure | Factory defect |  | 15699.955
Project MODEL 6 - COMPASS PH3 | Power Module (PM) | 5 | 1 | 18 | 5 | 14 | 2023 | 17 | 16 | 2 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 51 | Execution | 26 | Resources | Z - Other |  |  | Inexperienced staff | 5 | 0 | 0 | 1.6665 | 0.3333 | 224.9775 | Quality | Production | Medium | Execution | Z - Other | Inexperienced staff |  | 224.9775
Project MODEL 6 - COMPASS PH3 | Power Module (PM) | 5 | 1 | 18 | 5 | 14 | 2023 | 17 | 16 | 2 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 51 | Execution | 46 | Manufacturing | Z - Other |  |  | Incorrect installation | 12 | 0 | 0 | 3.9996 | 0.79992 | 539.946 | Schedule | Project Management | Low | Execution | Z - Other | Incorrect installation |  | 539.946
Project MODEL 6 - COMPASS PH3 | Power Module (PM) | 5 | 1 | 18 | 5 | 14 | 2023 | 17 | 16 | 2 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 51 | Energization | 38 | Resources | Z - Other |  |  | Lack coordination | 5 | 0 | 0 | 1.6665 | 0.3333 | 224.9775 | Schedule | Project Management | Medium | Energization | Z - Other | Lack coordination |  | 224.9775
Project MODEL 6 - COMPASS PH3 | Power Module (PM) | 5 | 1 | 18 | 5 | 14 | 2023 | 17 | 16 | 2 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 51 | Energization | 38 | Resources | Z - Other |  |  | Factory defect | 10 | 0 | 0 | 3.333 | 0.6666 | 449.955 | Schedule | Project Management | Low | Energization | Z - Other | Factory defect |  | 449.955
Project MODEL 6 - COMPASS PH3 | Power Module (PM) | 5 | 1 | 18 | 5 | 14 | 2023 | 17 | 16 | 2 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 51 | Commissioning | 42 | Resources | Z - Other |  |  | Lack coordination | 5 | 0 | 0 | 1.6665 | 0.3333 | 224.9775 | Schedule | Commissioning | Medium | Commissioning | Z - Other | Lack coordination |  | 224.9775
Project MODEL 6 - COMPASS PH3 | Power Module (PM) | 5 | 1 | 18 | 5 | 14 | 2023 | 17 | 16 | 2 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 51 | Commissioning | 43 | Resources | Z - Other |  |  | Missing support | 4 | 0 | 0 | 1.3332 | 0.26664 | 179.982 | Schedule | Commissioning | Low | Commissioning | Z - Other | Missing support |  | 179.982
[28 empty] | 0 | 0 | [10 empty] | 0
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Pre-Execution & Procurement | 2 | Design | Battery Cabinet/Rack |  | 67000 | Client rejection | 10 | 12060 | 1340 | 3.333 | 0.6666 | 449.955 | Cost | Engineering | Low | Pre-Execution & Procurement | Battery Cabinet/Rack | Client rejection |  | 13849.955
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Pre-Execution & Procurement | 2 | Drawings | Battery Cabinet/Rack |  | 67000 | Design change | 7 | 8442 | 938 | 2.3331 | 0.46662 | 314.9685 | Cost | Engineering | Low | Pre-Execution & Procurement | Battery Cabinet/Rack | Design change |  | 9694.9685
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Pre-Execution & Procurement | 2 | Design | Customer specifications |  |  | Design change | 7 | 0 | 0 | 2.3331 | 0.46662 | 314.9685 | Scope | Tendering | Low | Pre-Execution & Procurement | Customer specifications | Design change |  | 314.9685
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Pre-Execution & Procurement | 2 | Drawings | Cooling CRAH |  | 144500 | Design change | 7 | 18207 | 2023 | 2.3331 | 0.46662 | 314.9685 | Quality | Quality | Low | Pre-Execution & Procurement | Cooling CRAH | Design change |  | 20544.9685
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Pre-Execution & Procurement | 2 | Design | Cooling CRAH |  | 144500 | Design change | 7 | 18207 | 2023 | 2.3331 | 0.46662 | 314.9685 | Cost | Engineering | Low | Pre-Execution & Procurement | Cooling CRAH | Design change |  | 20544.9685
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Pre-Execution & Procurement | 2 | Customer & Site | Site Energized |  |  | Late delivery | 6 | 0 | 0 | 1.9998 | 0.39996 | 269.973 | Schedule | Project Management | Low | Pre-Execution & Procurement | Site Energized | Late delivery |  | 269.973
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Pre-Execution & Procurement | 3 | Change Requests | Battery Cabinet/Rack |  | 67000 | Design change | 7 | 8442 | 938 | 2.3331 | 0.46662 | 314.9685 | Quality | Tendering | High | Pre-Execution & Procurement | Battery Cabinet/Rack | Design change |  | 9694.9685
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Pre-Execution & Procurement | 3 | Change Requests | Main Panel A |  | 87000 | Design change | 7 | 10962 | 1218 | 2.3331 | 0.46662 | 314.9685 | Cost | Tendering | High | Pre-Execution & Procurement | Main Panel A | Design change |  | 12494.9685
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Pre-Execution & Procurement | 3 | Design | Cable tray type |  | 36500 | Design change | 7 | 4599 | 511 | 2.3331 | 0.46662 | 314.9685 | Cost | Project Management | Low | Pre-Execution & Procurement | Cable tray type | Design change |  | 5424.9685
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Pre-Execution & Procurement | 3 | Change Requests | Main Panel A |  | 87000 | Design change | 7 | 10962 | 1218 | 2.3331 | 0.46662 | 314.9685 | Cost | Tendering | Low | Pre-Execution & Procurement | Main Panel A | Design change |  | 12494.9685
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Pre-Execution & Procurement | 4 | Drawings | Cable tray structs |  | 14000 | Alignment error | 5 | 1260 | 140 | 1.6665 | 0.3333 | 224.9775 | Quality | Engineering | Low | Pre-Execution & Procurement | Cable tray structs | Alignment error |  | 1624.9775
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Pre-Execution & Procurement | 5 | Change Requests | Main Panel B |  | 78000 | Design change | 7 | 9828 | 1092 | 2.3331 | 0.46662 | 314.9685 | Cost | Engineering | High | Pre-Execution & Procurement | Main Panel B | Design change |  | 11234.9685
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Pre-Execution & Procurement | 6 | Drawings | Cable tray structs |  | 14000 | Alignment error | 5 | 1260 | 140 | 1.6665 | 0.3333 | 224.9775 | Cost | Engineering | Low | Pre-Execution & Procurement | Cable tray structs | Alignment error |  | 1624.9775
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Pre-Execution & Procurement | 6 | Change Requests | Medium voltage |  | 23000 | Design change | 7 | 2898 | 322 | 2.3331 | 0.46662 | 314.9685 | Cost | Tendering | Low | Pre-Execution & Procurement | Medium voltage | Design change |  | 3534.9685
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Pre-Execution & Procurement | 6 | Communication | Customer needs |  |  | Lack coordination | 5 | 0 | 0 | 1.6665 | 0.3333 | 224.9775 | Schedule | Project Management | Medium | Pre-Execution & Procurement | Customer needs | Lack coordination |  | 224.9775
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Pre-Execution & Procurement | 6 | Change Requests | Main Panel B |  | 78000 | Design change | 7 | 9828 | 1092 | 2.3331 | 0.46662 | 314.9685 | Quality | Project Management | Low | Pre-Execution & Procurement | Main Panel B | Design change |  | 11234.9685
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Pre-Execution & Procurement | 6 | Customer & Site | Site Energized |  | 36500 | Schedule delay | 9 | 5913 | 657 | 2.9997 | 0.59994 | 404.9595 | Schedule | Project Management | Low | Pre-Execution & Procurement | Site Energized | Schedule delay |  | 6974.9595
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Pre-Execution & Procurement | 6 | Drawings | Busbar |  | 24500 | Alignment error | 5 | 2205 | 245 | 1.6665 | 0.3333 | 224.9775 | Quality | Project Management | Low | Pre-Execution & Procurement | Busbar | Alignment error |  | 2674.9775
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Pre-Execution & Procurement | 6 | Communication | Battery LiThium |  | 102000 | Lack coordination | 5 | 9180 | 1020 | 1.6665 | 0.3333 | 224.9775 | Schedule | Tendering | Medium | Pre-Execution & Procurement | Battery LiThium | Lack coordination |  | 10424.9775
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Pre-Execution & Procurement | 6 | Design | Busbar |  | 24500 | Alignment error | 5 | 2205 | 245 | 1.6665 | 0.3333 | 224.9775 | Quality | Project Management | Low | Pre-Execution & Procurement | Busbar | Alignment error |  | 2674.9775
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Pre-Execution & Procurement | 6 | Change Requests | Floor Termination |  | 33500 | Ground failure | 4 | 2412 | 268 | 1.3332 | 0.26664 | 179.982 | Cost | Engineering | High | Pre-Execution & Procurement | Floor Termination | Ground failure |  | 2859.982
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Pre-Execution & Procurement | 6 | Design | Doors |  | 23000 | Alignment error | 5 | 2070 | 230 | 1.6665 | 0.3333 | 224.9775 | Quality | Engineering | Low | Pre-Execution & Procurement | Doors | Alignment error |  | 2524.9775
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Pre-Execution & Procurement | 7 | Change Requests | Structure |  | 132000 | Ground failure | 4 | 9504 | 1056 | 1.3332 | 0.26664 | 179.982 | Cost | Engineering | Low | Pre-Execution & Procurement | Structure | Ground failure |  | 10739.982
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Pre-Execution & Procurement | 7 | Drawings | Cable tray type |  | 36500 | Alignment error | 5 | 3285 | 365 | 1.6665 | 0.3333 | 224.9775 | Quality | Engineering | Medium | Pre-Execution & Procurement | Cable tray type | Alignment error |  | 3874.9775
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Pre-Execution & Procurement | 7 | Change Requests | Supply Chain |  | 77500 | No manual | 2 | 2790 | 310 | 0.6666 | 0.13332 | 89.991 | Quality | Project Management | Low | Pre-Execution & Procurement | Supply Chain | No manual |  | 3189.991
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Pre-Execution & Procurement | 8 | Communication | Customer needs |  |  | Communication failure | 7 | 0 | 0 | 2.3331 | 0.46662 | 314.9685 | Quality | Engineering | Low | Pre-Execution & Procurement | Customer needs | Communication failure |  | 314.9685
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Pre-Execution & Procurement | 9 | Change Requests | Signage Safety |  | 1500 | Configuration error | 6 | 162 | 18 | 1.9998 | 0.39996 | 269.973 | Quality | Engineering | High | Pre-Execution & Procurement | Signage Safety | Configuration error |  | 449.973
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Pre-Execution & Procurement | 9 | Change Requests | Cable grand |  | 1000 | Design change | 7 | 126 | 14 | 2.3331 | 0.46662 | 314.9685 | Quality | Engineering | Low | Pre-Execution & Procurement | Cable grand | Design change |  | 454.9685
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Pre-Execution & Procurement | 10 | Communication | Customer needs |  |  | Communication failure | 7 | 0 | 0 | 2.3331 | 0.46662 | 314.9685 | Quality | Project Management | Low | Pre-Execution & Procurement | Customer needs | Communication failure |  | 314.9685
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Pre-Execution & Procurement | 11 | Change Requests | Vertical support |  | 6500 | Alignment error | 5 | 585 | 65 | 1.6665 | 0.3333 | 224.9775 | Quality | Engineering | Low | Pre-Execution & Procurement | Vertical support | Alignment error |  | 874.9775
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Pre-Execution & Procurement | 13 | Contract | Customer specifications |  |  | Documentation error | 3 | 0 | 0 | 0.9999 | 0.19998 | 134.9865 | Quality | Tendering | Medium | Pre-Execution & Procurement | Customer specifications | Documentation error |  | 134.9865
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Pre-Execution & Procurement | 13 | Change Requests | Cable tray structs |  | 14000 | Alignment error | 5 | 1260 | 140 | 1.6665 | 0.3333 | 224.9775 | Quality | Project Management | Low | Pre-Execution & Procurement | Cable tray structs | Alignment error |  | 1624.9775
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Pre-Execution & Procurement | 13 | Submittal package | Customer specifications |  |  | Documentation error | 3 | 0 | 0 | 0.9999 | 0.19998 | 134.9865 | Quality | Engineering | Medium | Pre-Execution & Procurement | Customer specifications | Documentation error |  | 134.9865
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Pre-Execution & Procurement | 14 | Change Requests | Overhead Cooling |  | 104000 | Wrong drawings | 4 | 7488 | 832 | 1.3332 | 0.26664 | 179.982 | Cost | Project Management | Low | Pre-Execution & Procurement | Overhead Cooling | Wrong drawings |  | 8499.982
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Execution | 16 | Manufacturing | Structure |  | 132000 | Factory defect | 10 | 23760 | 2640 | 3.333 | 0.6666 | 449.955 | Cost | Project Management | Low | Execution | Structure | Factory defect |  | 26849.955
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Execution | 16 | Resources | Requiring site works |  |  | Z-Other | 5 | 0 | 0 | 1.6665 | 0.3333 | 224.9775 | Quality | Project Management | Low | Execution | Requiring site works | Z-Other |  | 224.9775
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Execution | 16 | Communication | Signage Safety |  | 3000 | Labeling error | 3 | 162 | 18 | 0.9999 | 0.19998 | 134.9865 | Quality | Project Management | Low | Execution | Signage Safety | Labeling error |  | 314.9865
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Execution | 16 | Technical Scope | Vertical support |  |  | Client rejection | 10 | 0 | 0 | 3.333 | 0.6666 | 449.955 | Scope | Engineering | Low | Execution | Vertical support | Client rejection |  | 449.955
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Execution | 18 | Resources | Customer specifications |  |  | Insulation failure | 6 | 0 | 0 | 1.9998 | 0.39996 | 269.973 | Quality | Project Management | Low | Execution | Customer specifications | Insulation failure |  | 269.973
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Execution | 21 | Change Requests | Floor Termination |  | 33500 | Incorrect installation | 12 | 7236 | 804 | 3.9996 | 0.79992 | 539.946 | Schedule | Project Management | Medium | Execution | Floor Termination | Incorrect installation |  | 8579.946
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Execution | 23 | Resources | Customer needs |  |  | Z-Other | 5 | 0 | 0 | 1.6665 | 0.3333 | 224.9775 | Schedule | Production | Low | Execution | Customer needs | Z-Other |  | 224.9775
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Execution | 24 | Resources | Customer specifications |  |  | Torque error | 3 | 0 | 0 | 0.9999 | 0.19998 | 134.9865 | Quality | Production | High | Execution | Customer specifications | Torque error |  | 134.9865
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Execution | 25 | Communication | Signage Safety |  | 3000 | Documentation error | 3 | 162 | 18 | 0.9999 | 0.19998 | 134.9865 | Quality | Project Management | Low | Execution | Signage Safety | Documentation error |  | 314.9865
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Execution | 26 | Resources | Customer needs |  |  | Torque error | 3 | 0 | 0 | 0.9999 | 0.19998 | 134.9865 | Schedule | Project Management | High | Execution | Customer needs | Torque error |  | 134.9865
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Execution | 26 | Drawings | Signage Safety |  | 3000 | Documentation error | 3 | 162 | 18 | 0.9999 | 0.19998 | 134.9865 | Quality | Project Management | Low | Execution | Signage Safety | Documentation error |  | 314.9865
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Execution | 28 | Resources | Requiring site works |  |  | Assembly error | 7 | 0 | 0 | 2.3331 | 0.46662 | 314.9685 | Cost | Project Management | Low | Execution | Requiring site works | Assembly error |  | 314.9685
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Shipping | 40 | Drawings | Floor Termination |  | 33500 | Assembly error | 7 | 4221 | 469 | 2.3331 | 0.46662 | 314.9685 | Quality | Engineering | Low | Shipping | Floor Termination | Assembly error |  | 5004.9685
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Shipping | 40 | Change Requests | Supply Chain |  |  | Incorrect installation | 12 | 0 | 0 | 3.9996 | 0.79992 | 539.946 | Cost | Engineering | Medium | Shipping | Supply Chain | Incorrect installation |  | 539.946
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Shipping | 40 | Price | Customer needs |  |  | Factory defect | 10 | 0 | 0 | 3.333 | 0.6666 | 449.955 | Quality | Project Management | Low | Shipping | Customer needs | Factory defect |  | 449.955
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Transport Duration | 42 | Communication | Battery LiThium |  | 102000 | Documentation error | 3 | 5508 | 612 | 0.9999 | 0.19998 | 134.9865 | Quality | Project Management | Medium | Transport Duration | Battery LiThium | Documentation error |  | 6254.9865
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Transport Duration | 43 | Change Requests | Site Readiness |  | 53000 | Safety error | 6 | 5724 | 636 | 1.9998 | 0.39996 | 269.973 | Schedule | Warehouse | High | Transport Duration | Site Readiness | Safety error |  | 6629.973
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Delivery on site | 44 | Communication | Site Readiness |  | 53000 | Transport damage | 8 | 7632 | 848 | 2.6664 | 0.53328 | 359.964 | Schedule | Project Management | High | Delivery on site | Site Readiness | Transport damage |  | 8839.964
Project MODEL 7 - DLR | Data Center (DC) | 2 | 1 | 18 | 14 | 9 | 2024 | 15 | 14 | 3 | 2 | 2 | LEVEL 3 | 1 | 2 | 2 | 2 | 1 | 44 | Delivery on site | 44 | Resources | Site Energized |  | 36500 | Schedule delay | 9 | 5913 | 657 | 2.9997 | 0.59994 | 404.9595 | Schedule | Project Management | Medium | Delivery on site | Site Energized | Schedule delay |  | 6974.9595
[28 empty] | 0 | 0 | [10 empty] | 0
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Pre-Execution & Procurement | 4 | Customer & Site | Site Readiness |  |  | Adverse weather | 5 | 0 | 0 | 1.6665 | 0.3333 | 224.9775 | Sales | Tendering | Medium | Pre-Execution & Procurement | Site Readiness | Adverse weather |  | 224.9775
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Pre-Execution & Procurement | 4 | Design | Main Panel A |  | 101500 | Configuration error | 6 | 10962 | 1218 | 1.9998 | 0.39996 | 269.973 | Cost | Engineering | Low | Pre-Execution & Procurement | Main Panel A | Configuration error |  | 12449.973
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Pre-Execution & Procurement | 5 | Communication | Customer specifications |  |  | Documentation error | 3 | 0 | 0 | 0.9999 | 0.19998 | 134.9865 | Quality | Tendering | Low | Pre-Execution & Procurement | Customer specifications | Documentation error |  | 134.9865
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Pre-Execution & Procurement | 7 | Design | Main Panel A |  | 101500 | Incorrect wiring | 9 | 16443 | 1827 | 2.9997 | 0.59994 | 404.9595 | Cost | Engineering | Low | Pre-Execution & Procurement | Main Panel A | Incorrect wiring |  | 18674.9595
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Pre-Execution & Procurement | 7 | Contract | Supply Chain |  | 56500 | No manual | 2 | 2034 | 226 | 0.6666 | 0.13332 | 89.991 | Quality | Tendering | High | Pre-Execution & Procurement | Supply Chain | No manual |  | 2349.991
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Pre-Execution & Procurement | 7 | Drawings | Cable grand |  | 4500 | Incorrect installation | 12 | 972 | 108 | 3.9996 | 0.79992 | 539.946 | Quality | Engineering | Medium | Pre-Execution & Procurement | Cable grand | Incorrect installation |  | 1619.946
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Pre-Execution & Procurement | 7 | Contract | Busbar |  | 64000 | Late delivery | 6 | 6912 | 768 | 1.9998 | 0.39996 | 269.973 | Cost | Project Management | Low | Pre-Execution & Procurement | Busbar | Late delivery |  | 7949.973
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Pre-Execution & Procurement | 8 | Design | Main Panel A |  | 101500 | Labeling error | 3 | 5481 | 609 | 0.9999 | 0.19998 | 134.9865 | Cost | Engineering | Low | Pre-Execution & Procurement | Main Panel A | Labeling error |  | 6224.9865
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Pre-Execution & Procurement | 9 | Customer & Site | Site Readiness |  |  | Connectivity failure | 7 | 0 | 0 | 2.3331 | 0.46662 | 314.9685 | Quality | Tendering | High | Pre-Execution & Procurement | Site Readiness | Connectivity failure |  | 314.9685
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Pre-Execution & Procurement | 10 | Communication | Enclosure |  | 56000 | Incompatible item | 7 | 7056 | 784 | 2.3331 | 0.46662 | 314.9685 | Cost | Tendering | Medium | Pre-Execution & Procurement | Enclosure | Incompatible item |  | 8154.9685
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Pre-Execution & Procurement | 11 | Submittal package | Doors |  | 45500 | External interference | 4 | 3276 | 364 | 1.3332 | 0.26664 | 179.982 | Cost | Tendering | High | Pre-Execution & Procurement | Doors | External interference |  | 3819.982
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Pre-Execution & Procurement | 11 | Change Requests | Main Panel A |  | 101500 | Missing kit | 5 | 9135 | 1015 | 1.6665 | 0.3333 | 224.9775 | Cost | Project Management | High | Pre-Execution & Procurement | Main Panel A | Missing kit |  | 10374.9775
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Pre-Execution & Procurement | 11 | Change Requests | Main Panel A |  | 101500 | Labeling error | 3 | 5481 | 609 | 0.9999 | 0.19998 | 134.9865 | Quality | Engineering | Medium | Pre-Execution & Procurement | Main Panel A | Labeling error |  | 6224.9865
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Pre-Execution & Procurement | 11 | Change Requests | PDU |  | 33500 | Late delivery | 6 | 3618 | 402 | 1.9998 | 0.39996 | 269.973 | Quality | Engineering | Low | Pre-Execution & Procurement | PDU | Late delivery |  | 4289.973
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Pre-Execution & Procurement | 11 | Change Requests | Cooling CRAH |  | 139500 | Lack coordination | 5 | 12555 | 1395 | 1.6665 | 0.3333 | 224.9775 | Cost | Engineering | Low | Pre-Execution & Procurement | Cooling CRAH | Lack coordination |  | 14174.9775
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Pre-Execution & Procurement | 11 | Design | Battery VRLA |  | 105000 | Late delivery | 6 | 11340 | 1260 | 1.9998 | 0.39996 | 269.973 | Cost | Engineering | High | Pre-Execution & Procurement | Battery VRLA | Late delivery |  | 12869.973
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Pre-Execution & Procurement | 13 | Transport/Logistics | Weather conditions |  |  | Adverse weather | 5 | 0 | 0 | 1.6665 | 0.3333 | 224.9775 | Sales | Project Management | Low | Pre-Execution & Procurement | Weather conditions | Adverse weather |  | 224.9775
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Pre-Execution & Procurement | 15 | Design | Main Panel A |  | 101500 | Late delivery | 6 | 10962 | 1218 | 1.9998 | 0.39996 | 269.973 | Schedule | Engineering | Low | Pre-Execution & Procurement | Main Panel A | Late delivery |  | 12449.973
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Pre-Execution & Procurement | 16 | Resources | Supplier need |  |  | Schedule delay | 9 | 0 | 0 | 2.9997 | 0.59994 | 404.9595 | Schedule | Project Management | Low | Pre-Execution & Procurement | Supplier need | Schedule delay |  | 404.9595
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Execution | 17 | Purchashing | Battery VRLA |  | 105000 | Schedule delay | 9 | 17010 | 1890 | 2.9997 | 0.59994 | 404.9595 | Cost | Production | High | Execution | Battery VRLA | Schedule delay |  | 19304.9595
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Execution | 18 | Drawings | Busbar |  | 64000 | Alignment error | 5 | 5760 | 640 | 1.6665 | 0.3333 | 224.9775 | Cost | Project Management | Low | Execution | Busbar | Alignment error |  | 6624.9775
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Execution | 18 | Transport/Logistics | Enclosure |  | 56000 | Packing error | 3 | 3024 | 336 | 0.9999 | 0.19998 | 134.9865 | Cost | Project Management | High | Execution | Enclosure | Packing error |  | 3494.9865
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Execution | 18 | Drawings | Enclosure |  | 56000 | Packing error | 3 | 3024 | 336 | 0.9999 | 0.19998 | 134.9865 | Quality | Project Management | Low | Execution | Enclosure | Packing error |  | 3494.9865
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Execution | 18 | Communication | Customer needs |  |  | Communication failure | 7 | 0 | 0 | 2.3331 | 0.46662 | 314.9685 | Quality | Production | Low | Execution | Customer needs | Communication failure |  | 314.9685
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Execution | 18 | Purchashing | Cable tray type |  | 12500 | Late delivery | 6 | 1350 | 150 | 1.9998 | 0.39996 | 269.973 | Schedule | Project Management | Low | Execution | Cable tray type | Late delivery |  | 1769.973
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Execution | 19 | Drawings | Cable tray type |  | 12500 | Schedule delay | 9 | 2025 | 225 | 2.9997 | 0.59994 | 404.9595 | Schedule | Production | Low | Execution | Cable tray type | Schedule delay |  | 2654.9595
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Execution | 20 | Purchashing | Doors |  | 45500 | Client rejection | 10 | 8190 | 910 | 3.333 | 0.6666 | 449.955 | Scope | Project Management | Low | Execution | Doors | Client rejection |  | 9549.955
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Execution | 21 | Purchashing | Cable type |  | 91500 | Schedule delay | 9 | 14823 | 1647 | 2.9997 | 0.59994 | 404.9595 | Schedule | Project Management | Low | Execution | Cable type | Schedule delay |  | 16874.9595
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Execution | 21 | Drawings | Cable grand |  | 4500 | Alignment error | 5 | 405 | 45 | 1.6665 | 0.3333 | 224.9775 | Cost | Project Management | Low | Execution | Cable grand | Alignment error |  | 674.9775
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Execution | 21 | Drawings | Cooling Inrow |  |  | Assembly error | 7 | 0 | 0 | 2.3331 | 0.46662 | 314.9685 | Quality | Production | Medium | Execution | Cooling Inrow | Assembly error |  | 314.9685
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Execution | 21 | Resources | Customer needs |  |  | Client rejection | 10 | 0 | 0 | 3.333 | 0.6666 | 449.955 | Scope | Project Management | Low | Execution | Customer needs | Client rejection |  | 449.955
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Execution | 21 | Communication | Customer needs |  |  | Communication failure | 7 | 0 | 0 | 2.3331 | 0.46662 | 314.9685 | Quality | Project Management | Low | Execution | Customer needs | Communication failure |  | 314.9685
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Execution | 21 | Quality | Floor Termination |  | 21500 | Insulation failure | 6 | 2322 | 258 | 1.9998 | 0.39996 | 269.973 | Cost | Production | High | Execution | Floor Termination | Insulation failure |  | 2849.973
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Execution | 23 | Drawings | Main Panel A |  | 101500 | Sensor error | 4 | 7308 | 812 | 1.3332 | 0.26664 | 179.982 | Cost | Project Management | Low | Execution | Main Panel A | Sensor error |  | 8299.982
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Execution | 24 | Drawings | Main Panel A |  | 101500 | Incorrect wiring | 9 | 16443 | 1827 | 2.9997 | 0.59994 | 404.9595 | Cost | Project Management | Medium | Execution | Main Panel A | Incorrect wiring |  | 18674.9595
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Execution | 26 | Resources | Cable type |  | 91500 | Incorrect installation | 12 | 19764 | 2196 | 3.9996 | 0.79992 | 539.946 | Cost | Production | Low | Execution | Cable type | Incorrect installation |  | 22499.946
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Execution | 26 | Resources | Cable type |  | 91500 | Incorrect wiring | 9 | 14823 | 1647 | 2.9997 | 0.59994 | 404.9595 | Quality | Project Management | Low | Execution | Cable type | Incorrect wiring |  | 16874.9595
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Execution | 30 | Purchashing | Enclosure |  | 56000 | Planning error | 6 | 6048 | 672 | 1.9998 | 0.39996 | 269.973 | Schedule | Project Management | Medium | Execution | Enclosure | Planning error |  | 6989.973
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Commissioning | 35 | Risk | Site Readiness |  |  | Planning error | 6 | 0 | 0 | 1.9998 | 0.39996 | 269.973 | Schedule | Project Management | Medium | Commissioning | Site Readiness | Planning error |  | 269.973
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Commissioning | 35 | Resources | Enclosure |  | 56000 | Alignment error | 5 | 5040 | 560 | 1.6665 | 0.3333 | 224.9775 | Cost | Commissioning | Low | Commissioning | Enclosure | Alignment error |  | 5824.9775
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Commissioning | 35 | Communication | Customer needs |  |  | Communication failure | 7 | 0 | 0 | 2.3331 | 0.46662 | 314.9685 | Quality | Commissioning | Low | Commissioning | Customer needs | Communication failure |  | 314.9685
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Shipping | 39 | Communication | Customer needs |  |  | Communication failure | 7 | 0 | 0 | 2.3331 | 0.46662 | 314.9685 | Quality | Project Management | Low | Shipping | Customer needs | Communication failure |  | 314.9685
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Shipping | 39 | Risk | Site Readiness |  |  | Schedule delay | 9 | 0 | 0 | 2.9997 | 0.59994 | 404.9595 | Schedule | Project Management | Low | Shipping | Site Readiness | Schedule delay |  | 404.9595
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Shipping | 39 | Risk | Site Readiness |  |  | Packing error | 3 | 0 | 0 | 0.9999 | 0.19998 | 134.9865 | Quality | Warehouse | Medium | Shipping | Site Readiness | Packing error |  | 134.9865
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Shipping | 39 | Communication | Customer needs |  |  | Communication failure | 7 | 0 | 0 | 2.3331 | 0.46662 | 314.9685 | Schedule | Warehouse | Low | Shipping | Customer needs | Communication failure |  | 314.9685
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Shipping | 39 | Communication | Customer specifications |  |  | Communication failure | 7 | 0 | 0 | 2.3331 | 0.46662 | 314.9685 | Schedule | Warehouse | Low | Shipping | Customer specifications | Communication failure |  | 314.9685
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Delivery on site | 42 | Transport/Logistics | Z - Other |  |  | Packing error | 3 | 0 | 0 | 0.9999 | 0.19998 | 134.9865 | Schedule | Project Management | Medium | Delivery on site | Z - Other | Packing error |  | 134.9865
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Delivery on site | 43 | Transport/Logistics | Z - Other |  |  | Route error | 4 | 0 | 0 | 1.3332 | 0.26664 | 179.982 | Quality | Project Management | Low | Delivery on site | Z - Other | Route error |  | 179.982
Project MODEL 8 - NNI1 | All-in-1 | 2 | 1 | 18 | 4 | 12 | 2025 | 16 | 16 | 1 | 1 | 2 | LEVEL 1 | 1 | 1 | 1 | 1 | 1 | 41 | Delivery on site | 43 | Safety | Weather conditions |  | 29000 | Adverse weather | 5 | 2610 | 290 | 1.6665 | 0.3333 | 224.9775 | Cost | Project Management | Low | Delivery on site | Weather conditions | Adverse weather |  | 3124.9775
[28 empty] | 0 | 0 | [10 empty] | 0
Project MODEL 9 - NND2 | All-in-1 | 2 | 1 | 18 | 2 | 40 | 2022 | 14 | 13 | 1 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Pre-Execution & Procurement | 3 | Design | Battery LiThium |  |  | Documentation error | 3 | 0 |  | 0.9999 | 0.19998 | 134.9865 |  |  |  | Pre-Execution & Procurement | Battery LiThium | Documentation error |  | 134.9865
Project MODEL 9 - NND2 | All-in-1 | 2 | 1 | 18 | 2 | 40 | 2022 | 14 | 13 | 1 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Pre-Execution & Procurement | 4 | Design | Battery Cabinet/Rack |  | 33500 | Alignment error | 5 | 3350 |  | 1.6665 | 0.3333 | 224.9775 |  |  |  | Pre-Execution & Procurement | Battery Cabinet/Rack | Alignment error |  | 3574.9775
Project MODEL 9 - NND2 | All-in-1 | 2 | 1 | 18 | 2 | 40 | 2022 | 14 | 13 | 1 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Pre-Execution & Procurement | 12 | Drawings | Cable grand |  | 2000 | Client rejection | 10 | 400 |  | 3.333 | 0.6666 | 449.955 |  |  |  | Pre-Execution & Procurement | Cable grand | Client rejection |  | 849.955
Project MODEL 9 - NND2 | All-in-1 | 2 | 1 | 18 | 2 | 40 | 2022 | 14 | 13 | 1 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Pre-Execution & Procurement | 15 | Change Requests | Cable grand |  | 2000 | Design change | 7 | 280 |  | 2.3331 | 0.46662 | 314.9685 |  |  |  | Pre-Execution & Procurement | Cable grand | Design change |  | 594.9685
Project MODEL 9 - NND2 | All-in-1 | 2 | 1 | 18 | 2 | 40 | 2022 | 14 | 13 | 1 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Pre-Execution & Procurement | 15 | Customer & Site | Site Energized |  |  | Schedule delay | 9 | 0 |  | 2.9997 | 0.59994 | 404.9595 |  |  |  | Pre-Execution & Procurement | Site Energized | Schedule delay |  | 404.9595
Project MODEL 9 - NND2 | All-in-1 | 2 | 1 | 18 | 2 | 40 | 2022 | 14 | 13 | 1 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Pre-Execution & Procurement | 14 | Purchashing | Battery VRLA |  | 54500 | Late delivery | 6 | 6540 |  | 1.9998 | 0.39996 | 269.973 |  |  |  | Pre-Execution & Procurement | Battery VRLA | Late delivery |  | 6809.973
Project MODEL 9 - NND2 | All-in-1 | 2 | 1 | 18 | 2 | 40 | 2022 | 14 | 13 | 1 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Execution | 16 | Change Requests | PDU |  | 11000 | Late delivery | 6 | 1320 |  | 1.9998 | 0.39996 | 269.973 |  |  |  | Execution | PDU | Late delivery |  | 1589.973
Project MODEL 9 - NND2 | All-in-1 | 2 | 1 | 18 | 2 | 40 | 2022 | 14 | 13 | 1 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Execution | 16 | Purchashing | Busbar |  | 32000 | Late delivery | 6 | 3840 |  | 1.9998 | 0.39996 | 269.973 |  |  |  | Execution | Busbar | Late delivery |  | 4109.973
Project MODEL 9 - NND2 | All-in-1 | 2 | 1 | 18 | 2 | 40 | 2022 | 14 | 13 | 1 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Execution | 16 | Change Requests | Cable tray type |  | 8000 | Late delivery | 6 | 960 |  | 1.9998 | 0.39996 | 269.973 |  |  |  | Execution | Cable tray type | Late delivery |  | 1229.973
Project MODEL 9 - NND2 | All-in-1 | 2 | 1 | 18 | 2 | 40 | 2022 | 14 | 13 | 1 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Execution | 16 | Purchashing | Doors |  | 23000 | Late delivery | 6 | 2760 |  | 1.9998 | 0.39996 | 269.973 |  |  |  | Execution | Doors | Late delivery |  | 3029.973
Project MODEL 9 - NND2 | All-in-1 | 2 | 1 | 18 | 2 | 40 | 2022 | 14 | 13 | 1 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Execution | 17 | Change Requests | Structure |  | 64000 | Late delivery | 6 | 7680 |  | 1.9998 | 0.39996 | 269.973 |  |  |  | Execution | Structure | Late delivery |  | 7949.973
Project MODEL 9 - NND2 | All-in-1 | 2 | 1 | 18 | 2 | 40 | 2022 | 14 | 13 | 1 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Execution | 19 | Purchashing | Cable grand |  | 2000 | Late delivery | 6 | 240 |  | 1.9998 | 0.39996 | 269.973 |  |  |  | Execution | Cable grand | Late delivery |  | 509.973
Project MODEL 9 - NND2 | All-in-1 | 2 | 1 | 18 | 2 | 40 | 2022 | 14 | 13 | 1 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Execution | 19 | Purchashing | Main Panel A |  | 65000 | Late delivery | 6 | 7800 |  | 1.9998 | 0.39996 | 269.973 |  |  |  | Execution | Main Panel A | Late delivery |  | 8069.973
Project MODEL 9 - NND2 | All-in-1 | 2 | 1 | 18 | 2 | 40 | 2022 | 14 | 13 | 1 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Execution | 19 | Communication | Customer needs |  |  | Communication failure | 7 | 0 |  | 2.3331 | 0.46662 | 314.9685 |  |  |  | Execution | Customer needs | Communication failure |  | 314.9685
Project MODEL 9 - NND2 | All-in-1 | 2 | 1 | 18 | 2 | 40 | 2022 | 14 | 13 | 1 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Execution | 19 | Quality | External Pannels |  | 12500 | Alignment error | 5 | 1250 |  | 1.6665 | 0.3333 | 224.9775 |  |  |  | Execution | External Pannels | Alignment error |  | 1474.9775
Project MODEL 9 - NND2 | All-in-1 | 2 | 1 | 18 | 2 | 40 | 2022 | 14 | 13 | 1 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Execution | 19 | Communication | Customer needs |  |  | Communication failure | 7 | 0 |  | 2.3331 | 0.46662 | 314.9685 |  |  |  | Execution | Customer needs | Communication failure |  | 314.9685
Project MODEL 9 - NND2 | All-in-1 | 2 | 1 | 18 | 2 | 40 | 2022 | 14 | 13 | 1 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Execution | 20 | Resources | Cable tray structs |  | 8000 | Alignment error | 5 | 800 |  | 1.6665 | 0.3333 | 224.9775 |  |  |  | Execution | Cable tray structs | Alignment error |  | 1024.9775
Project MODEL 9 - NND2 | All-in-1 | 2 | 1 | 18 | 2 | 40 | 2022 | 14 | 13 | 1 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Execution | 22 | Communication | Customer needs |  |  | Communication failure | 7 | 0 |  | 2.3331 | 0.46662 | 314.9685 |  |  |  | Execution | Customer needs | Communication failure |  | 314.9685
Project MODEL 9 - NND2 | All-in-1 | 2 | 1 | 18 | 2 | 40 | 2022 | 14 | 13 | 1 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Execution | 25 | Quality | Cooling Inrow |  | 23000 | Communication failure | 7 | 3220 |  | 2.3331 | 0.46662 | 314.9685 |  |  |  | Execution | Cooling Inrow | Communication failure |  | 3534.9685
Project MODEL 9 - NND2 | All-in-1 | 2 | 1 | 18 | 2 | 40 | 2022 | 14 | 13 | 1 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Execution | 25 | Resources | Supplier need |  |  | Schedule delay | 9 | 0 |  | 2.9997 | 0.59994 | 404.9595 |  |  |  | Execution | Supplier need | Schedule delay |  | 404.9595
Project MODEL 9 - NND2 | All-in-1 | 2 | 1 | 18 | 2 | 40 | 2022 | 14 | 13 | 1 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Execution | 26 | Resources | Customer needs |  |  | Client rejection | 10 | 0 |  | 3.333 | 0.6666 | 449.955 |  |  |  | Execution | Customer needs | Client rejection |  | 449.955
Project MODEL 9 - NND2 | All-in-1 | 2 | 1 | 18 | 2 | 40 | 2022 | 14 | 13 | 1 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Packiging | 32 | Resources | Enclosure |  | 56000 | Packing error | 3 | 3360 |  | 0.9999 | 0.19998 | 134.9865 |  |  |  | Packiging | Enclosure | Packing error |  | 3494.9865
Project MODEL 9 - NND2 | All-in-1 | 2 | 1 | 18 | 2 | 40 | 2022 | 14 | 13 | 1 | 1 | 2 | LEVEL 1 | 0 | 1 | 1 | 1 | 1 | 35 | Shipping | 33 | Drawings | External Pannels |  | 12500 | No signal | 3 | 750 |  | 0.9999 | 0.19998 | 134.9865 |  |  |  | Shipping | External Pannels | No signal |  | 884.9865
[19 empty] | 0 | [7 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 |  | 0
Project MODEL 10 - COMPASS PH4 | Power Module (PM) | 5 | 1 | 18 | 5 | 26 | 2023 | 10 | 13 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 42 | Pre-Execution & Procurement | 3 | Communication |  |  |  | Documentation error | 3 | 0 |  | 0.9999 | 0.19998 | 134.9865 |  |  |  | Pre-Execution & Procurement | 0 | Documentation error |  | 134.9865
Project MODEL 10 - COMPASS PH4 | Power Module (PM) | 5 | 1 | 18 | 5 | 26 | 2023 | 10 | 13 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 42 | Pre-Execution & Procurement | 8 | Change Requests | Requiring site works |  | 24500 | Needs rework | 11 | 13475 |  | 3.6663 | 0.73326 | 494.9505 |  |  |  | Pre-Execution & Procurement | Requiring site works | Needs rework |  | 13969.9505
Project MODEL 10 - COMPASS PH4 | Power Module (PM) | 5 | 1 | 18 | 5 | 26 | 2023 | 10 | 13 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 42 | Pre-Execution & Procurement | 9 | Submittal package |  |  |  | Documentation error | 3 | 0 |  | 0.9999 | 0.19998 | 134.9865 |  |  |  | Pre-Execution & Procurement | 0 | Documentation error |  | 134.9865
Project MODEL 10 - COMPASS PH4 | Power Module (PM) | 5 | 1 | 18 | 5 | 26 | 2023 | 10 | 13 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 42 | Pre-Execution & Procurement | 9 | Change Requests | Customer specifications |  | 120500 | Missing tests | 4 | 24100 |  | 1.3332 | 0.26664 | 179.982 |  |  |  | Pre-Execution & Procurement | Customer specifications | Missing tests |  | 24279.982
Project MODEL 10 - COMPASS PH4 | Power Module (PM) | 5 | 1 | 18 | 5 | 26 | 2023 | 10 | 13 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 42 | Execution | 12 | Resources | Z - Other |  |  | No supervision | 6 | 0 |  | 1.9998 | 0.39996 | 269.973 |  |  |  | Execution | Z - Other | No supervision |  | 269.973
Project MODEL 10 - COMPASS PH4 | Power Module (PM) | 5 | 1 | 18 | 5 | 26 | 2023 | 10 | 13 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 42 | Execution | 20 | Resources | Z - Other |  |  | No supervision | 6 | 0 |  | 1.9998 | 0.39996 | 269.973 |  |  |  | Execution | Z - Other | No supervision |  | 269.973
Project MODEL 10 - COMPASS PH4 | Power Module (PM) | 5 | 1 | 18 | 5 | 26 | 2023 | 10 | 13 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 42 | Execution | 21 | Resources | Z - Other |  |  | Lack coordination | 5 | 0 |  | 1.6665 | 0.3333 | 224.9775 |  |  |  | Execution | Z - Other | Lack coordination |  | 224.9775
Project MODEL 10 - COMPASS PH4 | Power Module (PM) | 5 | 1 | 18 | 5 | 26 | 2023 | 10 | 13 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 42 | Execution | 22 | Resources | Z - Other |  |  | Ground failure | 4 | 0 |  | 1.3332 | 0.26664 | 179.982 |  |  |  | Execution | Z - Other | Ground failure |  | 179.982
Project MODEL 10 - COMPASS PH4 | Power Module (PM) | 5 | 1 | 18 | 5 | 26 | 2023 | 10 | 13 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 42 | Transport Duration | 41 | Contract | Supply Chain |  |  | Client rejection | 10 | 0 |  | 3.333 | 0.6666 | 449.955 |  |  |  | Transport Duration | Supply Chain | Client rejection |  | 449.955
Project MODEL 10 - COMPASS PH4 | Power Module (PM) | 5 | 1 | 18 | 5 | 26 | 2023 | 10 | 13 | 3 | 4 | 5 | LEVEL 4 | 0 | 3 | 1 | 2 | 1 | 42 | Transport Duration | 41 | Drawings | Z - Other |  |  | Wrong documentation | 3 | 0 |  | 0.9999 | 0.19998 | 134.9865 |  |  |  | Transport Duration | Z - Other | Wrong documentation |  | 134.9865
[32 empty] | 0 |  |  |  | 0 | 0 | 0 |  | 0
Project MODEL 11 - ELI LILLY 2 | All-in-1 | 2 | 1 | 18 | 4 | 47 | 2024 | 13 | 13 | 2 | 2 | 2 | LEVEL 1 | 1 | 2 | 1 | 1 | 1 | 38 | Pre-Execution & Procurement | 2 | Design | Main Panel A |  | 98500 | Alignment error | 5 | 8865 | 985 | 1.6665 | 0.3333 | 224.9775 | Cost | Engineering | Low | Pre-Execution & Procurement | Main Panel A | Alignment error |  | 10074.9775
Project MODEL 11 - ELI LILLY 2 | All-in-1 | 2 | 1 | 18 | 4 | 47 | 2024 | 13 | 13 | 2 | 2 | 2 | LEVEL 1 | 1 | 2 | 1 | 1 | 1 | 38 | Pre-Execution & Procurement | 4 | Design | Cable tray structs |  | 56000 | Alignment error | 5 | 5040 | 560 | 1.6665 | 0.3333 | 224.9775 | Quality | Engineering | Low | Pre-Execution & Procurement | Cable tray structs | Alignment error |  | 5824.9775
Project MODEL 11 - ELI LILLY 2 | All-in-1 | 2 | 1 | 18 | 4 | 47 | 2024 | 13 | 13 | 2 | 2 | 2 | LEVEL 1 | 1 | 2 | 1 | 1 | 1 | 38 | Pre-Execution & Procurement | 6 | Drawings | Busbar |  | 66000 | Wrong material | 6 | 7128 | 792 | 1.9998 | 0.39996 | 269.973 | Schedule | Engineering | High | Pre-Execution & Procurement | Busbar | Wrong material |  | 8189.973
Project MODEL 11 - ELI LILLY 2 | All-in-1 | 2 | 1 | 18 | 4 | 47 | 2024 | 13 | 13 | 2 | 2 | 2 | LEVEL 1 | 1 | 2 | 1 | 1 | 1 | 38 | Pre-Execution & Procurement | 6 | Change Requests | Main Panel A |  | 98500 | Late delivery | 6 | 10638 | 1182 | 1.9998 | 0.39996 | 269.973 | Cost | Engineering | High | Pre-Execution & Procurement | Main Panel A | Late delivery |  | 12089.973
Project MODEL 11 - ELI LILLY 2 | All-in-1 | 2 | 1 | 18 | 4 | 47 | 2024 | 13 | 13 | 2 | 2 | 2 | LEVEL 1 | 1 | 2 | 1 | 1 | 1 | 38 | Pre-Execution & Procurement | 6 | Purchashing | Battery VRLA |  | 105000 | Schedule delay | 9 | 17010 | 1890 | 2.9997 | 0.59994 | 404.9595 | Cost | Tendering | High | Pre-Execution & Procurement | Battery VRLA | Schedule delay |  | 19304.9595
Project MODEL 11 - ELI LILLY 2 | All-in-1 | 2 | 1 | 18 | 4 | 47 | 2024 | 13 | 13 | 2 | 2 | 2 | LEVEL 1 | 1 | 2 | 1 | 1 | 1 | 38 | Pre-Execution & Procurement | 7 | Change Requests | Cable tray structs |  | 56000 | Missing kit | 5 | 5040 | 560 | 1.6665 | 0.3333 | 224.9775 | Quality | Engineering | Low | Pre-Execution & Procurement | Cable tray structs | Missing kit |  | 5824.9775
Project MODEL 11 - ELI LILLY 2 | All-in-1 | 2 | 1 | 18 | 4 | 47 | 2024 | 13 | 13 | 2 | 2 | 2 | LEVEL 1 | 1 | 2 | 1 | 1 | 1 | 38 | Pre-Execution & Procurement | 8 | Drawings | Main Panel A |  | 98500 | Labeling error | 3 | 5319 | 591 | 0.9999 | 0.19998 | 134.9865 | Cost | Engineering | Low | Pre-Execution & Procurement | Main Panel A | Labeling error |  | 6044.9865
Project MODEL 11 - ELI LILLY 2 | All-in-1 | 2 | 1 | 18 | 4 | 47 | 2024 | 13 | 13 | 2 | 2 | 2 | LEVEL 1 | 1 | 2 | 1 | 1 | 1 | 38 | Pre-Execution & Procurement | 9 | Change Requests | Doors |  | 50000 | Late delivery | 6 | 5400 | 600 | 1.9998 | 0.39996 | 269.973 | Schedule | Project Management | Low | Pre-Execution & Procurement | Doors | Late delivery |  | 6269.973
Project MODEL 11 - ELI LILLY 2 | All-in-1 | 2 | 1 | 18 | 4 | 47 | 2024 | 13 | 13 | 2 | 2 | 2 | LEVEL 1 | 1 | 2 | 1 | 1 | 1 | 38 | Pre-Execution & Procurement | 10 | Design | Busbar |  | 66000 | Missing signage | 2 | 2376 | 264 | 0.6666 | 0.13332 | 89.991 | Quality | Engineering | Low | Pre-Execution & Procurement | Busbar | Missing signage |  | 2729.991
Project MODEL 11 - ELI LILLY 2 | All-in-1 | 2 | 1 | 18 | 4 | 47 | 2024 | 13 | 13 | 2 | 2 | 2 | LEVEL 1 | 1 | 2 | 1 | 1 | 1 | 38 | Pre-Execution & Procurement | 11 | Submittal package | Main Panel A |  | 98500 | Late delivery | 6 | 10638 | 1182 | 1.9998 | 0.39996 | 269.973 | Schedule | Engineering | High | Pre-Execution & Procurement | Main Panel A | Late delivery |  | 12089.973
Project MODEL 11 - ELI LILLY 2 | All-in-1 | 2 | 1 | 18 | 4 | 47 | 2024 | 13 | 13 | 2 | 2 | 2 | LEVEL 1 | 1 | 2 | 1 | 1 | 1 | 38 | Pre-Execution & Procurement | 12 | Change Requests | Enclosure |  | 56000 | Planning error | 6 | 6048 | 672 | 1.9998 | 0.39996 | 269.973 | Schedule | Tendering | Low | Pre-Execution & Procurement | Enclosure | Planning error |  | 6989.973
Project MODEL 11 - ELI LILLY 2 | All-in-1 | 2 | 1 | 18 | 4 | 47 | 2024 | 13 | 13 | 2 | 2 | 2 | LEVEL 1 | 1 | 2 | 1 | 1 | 1 | 38 | Pre-Execution & Procurement | 12 | Change Requests | Cable grand |  | 4500 | Incorrect installation | 12 | 972 | 108 | 3.9996 | 0.79992 | 539.946 | Quality | Engineering | Medium | Pre-Execution & Procurement | Cable grand | Incorrect installation |  | 1619.946
Project MODEL 11 - ELI LILLY 2 | All-in-1 | 2 | 1 | 18 | 4 | 47 | 2024 | 13 | 13 | 2 | 2 | 2 | LEVEL 1 | 1 | 2 | 1 | 1 | 1 | 38 | Pre-Execution & Procurement | 13 | Drawings | Main Panel A |  | 98500 | Late delivery | 6 | 10638 | 1182 | 1.9998 | 0.39996 | 269.973 | Schedule | Engineering | Low | Pre-Execution & Procurement | Main Panel A | Late delivery |  | 12089.973
Project MODEL 11 - ELI LILLY 2 | All-in-1 | 2 | 1 | 18 | 4 | 47 | 2024 | 13 | 13 | 2 | 2 | 2 | LEVEL 1 | 1 | 2 | 1 | 1 | 1 | 38 | Execution | 15 | Drawings | Doors |  | 50000 | Late delivery | 6 | 5400 | 600 | 1.9998 | 0.39996 | 269.973 | Schedule | Production | Low | Execution | Doors | Late delivery |  | 6269.973
Project MODEL 11 - ELI LILLY 2 | All-in-1 | 2 | 1 | 18 | 4 | 47 | 2024 | 13 | 13 | 2 | 2 | 2 | LEVEL 1 | 1 | 2 | 1 | 1 | 1 | 38 | Execution | 17 | Communication | Customer needs |  |  | Communication failure | 7 | 0 | 0 | 2.3331 | 0.46662 | 314.9685 | Quality | Project Management | Low | Execution | Customer needs | Communication failure |  | 314.9685
Project MODEL 11 - ELI LILLY 2 | All-in-1 | 2 | 1 | 18 | 4 | 47 | 2024 | 13 | 13 | 2 | 2 | 2 | LEVEL 1 | 1 | 2 | 1 | 1 | 1 | 38 | Execution | 17 | Purchashing | Doors |  | 50000 | Schedule delay | 9 | 8100 | 900 | 2.9997 | 0.59994 | 404.9595 | Schedule | Engineering | Low | Execution | Doors | Schedule delay |  | 9404.9595
Project MODEL 11 - ELI LILLY 2 | All-in-1 | 2 | 1 | 18 | 4 | 47 | 2024 | 13 | 13 | 2 | 2 | 2 | LEVEL 1 | 1 | 2 | 1 | 1 | 1 | 38 | Execution | 17 | Purchashing | Cable type |  | 91500 | Schedule delay | 9 | 14823 | 1647 | 2.9997 | 0.59994 | 404.9595 | Schedule | Engineering | High | Execution | Cable type | Schedule delay |  | 16874.9595
Project MODEL 11 - ELI LILLY 2 | All-in-1 | 2 | 1 | 18 | 4 | 47 | 2024 | 13 | 13 | 2 | 2 | 2 | LEVEL 1 | 1 | 2 | 1 | 1 | 1 | 38 | Execution | 17 | Communication | Customer needs |  |  | Communication failure | 7 | 0 | 0 | 2.3331 | 0.46662 | 314.9685 | Quality | Project Management | Low | Execution | Customer needs | Communication failure |  | 314.9685
Project MODEL 11 - ELI LILLY 2 | All-in-1 | 2 | 1 | 18 | 4 | 47 | 2024 | 13 | 13 | 2 | 2 | 2 | LEVEL 1 | 1 | 2 | 1 | 1 | 1 | 38 | Execution | 17 | Customer & Site | Site Readiness |  |  | Connectivity failure | 7 | 0 | 0 | 2.3331 | 0.46662 | 314.9685 | Quality | Project Management | Low | Execution | Site Readiness | Connectivity failure |  | 314.9685
Project MODEL 11 - ELI LILLY 2 | All-in-1 | 2 | 1 | 18 | 4 | 47 | 2024 | 13 | 13 | 2 | 2 | 2 | LEVEL 1 | 1 | 2 | 1 | 1 | 1 | 38 | Execution | 18 | Manufacturing | Busbar |  | 66000 | Assembly error | 7 | 8316 | 924 | 2.3331 | 0.46662 | 314.9685 | Quality | Production | Low | Execution | Busbar | Assembly error |  | 9554.9685
Project MODEL 11 - ELI LILLY 2 | All-in-1 | 2 | 1 | 18 | 4 | 47 | 2024 | 13 | 13 | 2 | 2 | 2 | LEVEL 1 | 1 | 2 | 1 | 1 | 1 | 38 | Execution | 21 | Safety | Doors |  | 50000 | Late delivery | 6 | 5400 | 600 | 1.9998 | 0.39996 | 269.973 | Schedule | Project Management | Low | Execution | Doors | Late delivery |  | 6269.973
Project MODEL 11 - ELI LILLY 2 | All-in-1 | 2 | 1 | 18 | 4 | 47 | 2024 | 13 | 13 | 2 | 2 | 2 | LEVEL 1 | 1 | 2 | 1 | 1 | 1 | 38 | Execution | 23 | Resources | Cable type |  | 91500 | Design change | 7 | 11529 | 1281 | 2.3331 | 0.46662 | 314.9685 | Cost | Project Management | High | Execution | Cable type | Design change |  | 13124.9685
Project MODEL 11 - ELI LILLY 2 | All-in-1 | 2 | 1 | 18 | 4 | 47 | 2024 | 13 | 13 | 2 | 2 | 2 | LEVEL 1 | 1 | 2 | 1 | 1 | 1 | 38 | Execution | 25 | Customer & Site | Site Energized |  |  | Lack coordination | 5 | 0 | 0 | 1.6665 | 0.3333 | 224.9775 | Quality | Project Management | Medium | Execution | Site Energized | Lack coordination |  | 224.9775
Project MODEL 11 - ELI LILLY 2 | All-in-1 | 2 | 1 | 18 | 4 | 47 | 2024 | 13 | 13 | 2 | 2 | 2 | LEVEL 1 | 1 | 2 | 1 | 1 | 1 | 38 | Energization | 30 | Resources | Z - Other |  |  | Late delivery | 6 | 0 | 0 | 1.9998 | 0.39996 | 269.973 | Schedule | Project Management | Low | Energization | Z - Other | Late delivery |  | 269.973
Project MODEL 11 - ELI LILLY 2 | All-in-1 | 2 | 1 | 18 | 4 | 47 | 2024 | 13 | 13 | 2 | 2 | 2 | LEVEL 1 | 1 | 2 | 1 | 1 | 1 | 38 | Shipping | 36 | Drawings | Structure |  |  | Factory defect | 10 | 0 | 0 | 3.333 | 0.6666 | 449.955 | Schedule | Warehouse | Low | Shipping | Structure | Factory defect |  | 449.955
Project MODEL 11 - ELI LILLY 2 | All-in-1 | 2 | 1 | 18 | 4 | 47 | 2024 | 13 | 13 | 2 | 2 | 2 | LEVEL 1 | 1 | 2 | 1 | 1 | 1 | 38 | Transport Duration | 37 | Communication | Z - Other |  |  | Schedule delay | 9 | 0 | 0 | 2.9997 | 0.59994 | 404.9595 | Schedule | Production | Low | Transport Duration | Z - Other | Schedule delay |  | 404.9595
[28 empty] | 0 | 0 | [10 empty] | 0
Project MODEL 12 - NND6 | All-in-1 | 1 | 1 | 18 | 1 | 9 | 2025 | 10 | 14 | 2 | 2 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 35 | Pre-Execution & Procurement | 2 | Bill of Material | Z - Other |  |  | Wrong documentation | 3 | 0 | 0 | 0.9999 | 0.19998 | 134.9865 | Quality | Tendering | Low | Pre-Execution & Procurement | Z - Other | Wrong documentation |  | 134.9865
Project MODEL 12 - NND6 | All-in-1 | 1 | 1 | 18 | 1 | 9 | 2025 | 10 | 14 | 2 | 2 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 35 | Pre-Execution & Procurement | 5 | Drawings | Battery Cabinet/Rack |  | 27500 | Alignment error | 5 | 1237.5 | 137.5 | 1.6665 | 0.3333 | 224.9775 | Quality | Engineering | Low | Pre-Execution & Procurement | Battery Cabinet/Rack | Alignment error |  | 1599.9775
Project MODEL 12 - NND6 | All-in-1 | 1 | 1 | 18 | 1 | 9 | 2025 | 10 | 14 | 2 | 2 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 35 | Pre-Execution & Procurement | 6 | Design | Battery VRLA |  | 89500 | Late delivery | 6 | 4833 | 537 | 1.9998 | 0.39996 | 269.973 | Cost | Engineering | High | Pre-Execution & Procurement | Battery VRLA | Late delivery |  | 5639.973
Project MODEL 12 - NND6 | All-in-1 | 1 | 1 | 18 | 1 | 9 | 2025 | 10 | 14 | 2 | 2 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 35 | Pre-Execution & Procurement | 6 | Design | Cable grand |  | 3000 | Alignment error | 5 | 135 | 15 | 1.6665 | 0.3333 | 224.9775 | Cost | Engineering | Low | Pre-Execution & Procurement | Cable grand | Alignment error |  | 374.9775
Project MODEL 12 - NND6 | All-in-1 | 1 | 1 | 18 | 1 | 9 | 2025 | 10 | 14 | 2 | 2 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 35 | Pre-Execution & Procurement | 6 | Design | Netbots |  | 12500 | Configuration error | 6 | 675 | 75 | 1.9998 | 0.39996 | 269.973 | Quality | Engineering | Low | Pre-Execution & Procurement | Netbots | Configuration error |  | 1019.973
Project MODEL 12 - NND6 | All-in-1 | 1 | 1 | 18 | 1 | 9 | 2025 | 10 | 14 | 2 | 2 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 35 | Pre-Execution & Procurement | 6 | Change Requests | Doors |  | 23000 | Alignment error | 5 | 1035 | 115 | 1.6665 | 0.3333 | 224.9775 | Quality | Tendering | Medium | Pre-Execution & Procurement | Doors | Alignment error |  | 1374.9775
Project MODEL 12 - NND6 | All-in-1 | 1 | 1 | 18 | 1 | 9 | 2025 | 10 | 14 | 2 | 2 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 35 | Pre-Execution & Procurement | 6 | Technical Scope | External Pannels |  | 32000 | Protocol error | 4 | 1152 | 128 | 1.3332 | 0.26664 | 179.982 | Quality | Tendering | Medium | Pre-Execution & Procurement | External Pannels | Protocol error |  | 1459.982
Project MODEL 12 - NND6 | All-in-1 | 1 | 1 | 18 | 1 | 9 | 2025 | 10 | 14 | 2 | 2 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 35 | Pre-Execution & Procurement | 6 | Bill of Material | Z - Other |  |  | Documentation error | 3 | 0 | 0 | 0.9999 | 0.19998 | 134.9865 | Quality | Tendering | Low | Pre-Execution & Procurement | Z - Other | Documentation error |  | 134.9865
Project MODEL 12 - NND6 | All-in-1 | 1 | 1 | 18 | 1 | 9 | 2025 | 10 | 14 | 2 | 2 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 35 | Pre-Execution & Procurement | 6 | Customer & Site | Site Energized |  |  | Schedule delay | 9 | 0 | 0 | 2.9997 | 0.59994 | 404.9595 | Schedule | Tendering | Low | Pre-Execution & Procurement | Site Energized | Schedule delay |  | 404.9595
Project MODEL 12 - NND6 | All-in-1 | 1 | 1 | 18 | 1 | 9 | 2025 | 10 | 14 | 2 | 2 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 35 | Pre-Execution & Procurement | 6 | Change Requests | Switchboard |  |  | Schedule delay | 9 | 0 | 0 | 2.9997 | 0.59994 | 404.9595 | Schedule | Tendering | Low | Pre-Execution & Procurement | Switchboard | Schedule delay |  | 404.9595
Project MODEL 12 - NND6 | All-in-1 | 1 | 1 | 18 | 1 | 9 | 2025 | 10 | 14 | 2 | 2 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 35 | Pre-Execution & Procurement | 6 | Contract | Site Energized |  |  | Schedule delay | 9 | 0 | 0 | 2.9997 | 0.59994 | 404.9595 | Schedule | Tendering | Low | Pre-Execution & Procurement | Site Energized | Schedule delay |  | 404.9595
Project MODEL 12 - NND6 | All-in-1 | 1 | 1 | 18 | 1 | 9 | 2025 | 10 | 14 | 2 | 2 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 35 | Pre-Execution & Procurement | 7 | Communication | Customer needs |  |  | Communication failure | 7 | 0 | 0 | 2.3331 | 0.46662 | 314.9685 | Sales | Project Management | Low | Pre-Execution & Procurement | Customer needs | Communication failure |  | 314.9685
Project MODEL 12 - NND6 | All-in-1 | 1 | 1 | 18 | 1 | 9 | 2025 | 10 | 14 | 2 | 2 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 35 | Pre-Execution & Procurement | 8 | Submittal package | Cable type |  | 67000 | Wrong material | 6 | 3618 | 402 | 1.9998 | 0.39996 | 269.973 | Quality | Engineering | Medium | Pre-Execution & Procurement | Cable type | Wrong material |  | 4289.973
Project MODEL 12 - NND6 | All-in-1 | 1 | 1 | 18 | 1 | 9 | 2025 | 10 | 14 | 2 | 2 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 35 | Pre-Execution & Procurement | 8 | Change Requests | Switchboard |  | 87000 | Configuration error | 6 | 4698 | 522 | 1.9998 | 0.39996 | 269.973 | Cost | Project Management | High | Pre-Execution & Procurement | Switchboard | Configuration error |  | 5489.973
Project MODEL 12 - NND6 | All-in-1 | 1 | 1 | 18 | 1 | 9 | 2025 | 10 | 14 | 2 | 2 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 35 | Pre-Execution & Procurement | 10 | Change Requests | Battery Cabinet/Rack |  | 27500 | Design change | 7 | 1732.5 | 192.5 | 2.3331 | 0.46662 | 314.9685 | Cost | Project Management | Low | Pre-Execution & Procurement | Battery Cabinet/Rack | Design change |  | 2239.9685
Project MODEL 12 - NND6 | All-in-1 | 1 | 1 | 18 | 1 | 9 | 2025 | 10 | 14 | 2 | 2 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 35 | Execution | 13 | Purchashing | Doors |  | 23000 | Incorrect installation | 12 | 2484 | 276 | 3.9996 | 0.79992 | 539.946 | Quality | Engineering | High | Execution | Doors | Incorrect installation |  | 3299.946
Project MODEL 12 - NND6 | All-in-1 | 1 | 1 | 18 | 1 | 9 | 2025 | 10 | 14 | 2 | 2 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 35 | Execution | 13 | Communication | Signage Safety |  | 3500 | Labeling error | 3 | 94.5 | 10.5 | 0.9999 | 0.19998 | 134.9865 | Quality | Engineering | Low | Execution | Signage Safety | Labeling error |  | 239.9865
Project MODEL 13 - NND5 | All-in-1 | 1 | 1 | 18 | 1 | 9 | 2025 | 10 | 14 | 2 | 2 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 35 | Execution | 13 | Drawings | Cooling Inrow |  | 33500 | Missing kit | 5 | 1507.5 | 167.5 | 1.6665 | 0.3333 | 224.9775 | Quality | Production | Low | Execution | Cooling Inrow | Missing kit |  | 1899.9775
Project MODEL 12 - NND6 | All-in-1 | 1 | 1 | 18 | 1 | 9 | 2025 | 10 | 14 | 2 | 2 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 35 | Execution | 13 | Purchashing | External Pannels |  | 32000 | Late delivery | 6 | 1728 | 192 | 1.9998 | 0.39996 | 269.973 | Schedule | Project Management | Low | Execution | External Pannels | Late delivery |  | 2189.973
Project MODEL 12 - NND6 | All-in-1 | 1 | 1 | 18 | 1 | 9 | 2025 | 10 | 14 | 2 | 2 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 35 | Execution | 14 | Drawings | Battery Cabinet/Rack |  | 27500 | Late delivery | 6 | 1485 | 165 | 1.9998 | 0.39996 | 269.973 | Schedule | Project Management | Low | Execution | Battery Cabinet/Rack | Late delivery |  | 1919.973
Project MODEL 12 - NND6 | All-in-1 | 1 | 1 | 18 | 1 | 9 | 2025 | 10 | 14 | 2 | 2 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 35 | Execution | 16 | Resources | Switchboard |  | 87000 | Assembly error | 7 | 5481 | 609 | 2.3331 | 0.46662 | 314.9685 | Quality | Project Management | Medium | Execution | Switchboard | Assembly error |  | 6404.9685
Project MODEL 12 - NND6 | All-in-1 | 1 | 1 | 18 | 1 | 9 | 2025 | 10 | 14 | 2 | 2 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 35 | Execution | 16 | Communication | Customer needs |  |  | Communication failure | 7 | 0 | 0 | 2.3331 | 0.46662 | 314.9685 | Quality | Project Management | Low | Execution | Customer needs | Communication failure |  | 314.9685
Project MODEL 12 - NND6 | All-in-1 | 1 | 1 | 18 | 1 | 9 | 2025 | 10 | 14 | 2 | 2 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 35 | Execution | 16 | Resources | Cable type |  | 67000 | Design change | 7 | 4221 | 469 | 2.3331 | 0.46662 | 314.9685 | Cost | Production | High | Execution | Cable type | Design change |  | 5004.9685
Project MODEL 12 - NND6 | All-in-1 | 1 | 1 | 18 | 1 | 9 | 2025 | 10 | 14 | 2 | 2 | 2 | LEVEL 1 | 0 | 2 | 1 | 1 | 1 | 35 | Commissioning | 30 | Resources | Switchboard |  | 87000 | Torque error | 3 | 2349 | 261 | 0.9999 | 0.19998 | 134.9865 | Quality | Commissioning | High | Commissioning | Switchboard | Torque error |  | 2744.9865
[28 empty] | 0 | 0 | [10 empty] | 0
Project MODEL 14 - IRIDIUM | Skid | 1 | 0 | 10 | 2 | 2 | 2025 | 14 | 19 | 5 | 4 | 4 | LEVEL 1 | 0 | 3 | 3 | 2 | 2 | 56 | Pre-Execution & Procurement | 2 | Change Requests | Structure |  | 35000 | Design change | 7 | 2205 | 245 | 2.3331 | 0.46662 | 314.9685 | Cost | Tendering | Low | Pre-Execution & Procurement | Structure | Design change |  | 2764.9685
Project MODEL 14 - IRIDIUM | Skid | 1 | 0 | 10 | 2 | 2 | 2025 | 14 | 19 | 5 | 4 | 4 | LEVEL 1 | 0 | 3 | 3 | 2 | 2 | 56 | Pre-Execution & Procurement | 4 | Seismic Level | Structure |  | 35000 | Design change | 7 | 2205 | 245 | 2.3331 | 0.46662 | 314.9685 | Cost | Tendering | Low | Pre-Execution & Procurement | Structure | Design change |  | 2764.9685
Project MODEL 14 - IRIDIUM | Skid | 1 | 0 | 10 | 2 | 2 | 2025 | 14 | 19 | 5 | 4 | 4 | LEVEL 1 | 0 | 3 | 3 | 2 | 2 | 56 | Pre-Execution & Procurement | 5 | Change Requests | Structure |  | 35000 | Design change | 7 | 2205 | 245 | 2.3331 | 0.46662 | 314.9685 | Cost | Tendering | Low | Pre-Execution & Procurement | Structure | Design change |  | 2764.9685
Project MODEL 14 - IRIDIUM | Skid | 1 | 0 | 10 | 2 | 2 | 2025 | 14 | 19 | 5 | 4 | 4 | LEVEL 1 | 0 | 3 | 3 | 2 | 2 | 56 | Pre-Execution & Procurement | 5 | Change Requests | UPS |  | 54000 | Missing tests | 4 | 1944 | 216 | 1.3332 | 0.26664 | 179.982 | Cost | Tendering | Low | Pre-Execution & Procurement | UPS | Missing tests |  | 2339.982
Project MODEL 14 - IRIDIUM | Skid | 1 | 0 | 10 | 2 | 2 | 2025 | 14 | 19 | 5 | 4 | 4 | LEVEL 1 | 0 | 3 | 3 | 2 | 2 | 56 | Pre-Execution & Procurement | 6 | Seismic Level | Structure |  | 35000 | Design change | 7 | 2205 | 245 | 2.3331 | 0.46662 | 314.9685 | Cost | Engineering | Low | Pre-Execution & Procurement | Structure | Design change |  | 2764.9685
Project MODEL 14 - IRIDIUM | Skid | 1 | 0 | 10 | 2 | 2 | 2025 | 14 | 19 | 5 | 4 | 4 | LEVEL 1 | 0 | 3 | 3 | 2 | 2 | 56 | Pre-Execution & Procurement | 8 | Change Requests | Main Panel A |  | 65000 | Language error | 3 | 1755 | 195 | 0.9999 | 0.19998 | 134.9865 | Cost | Tendering | Medium | Pre-Execution & Procurement | Main Panel A | Language error |  | 2084.9865
Project MODEL 14 - IRIDIUM | Skid | 1 | 0 | 10 | 2 | 2 | 2025 | 14 | 19 | 5 | 4 | 4 | LEVEL 1 | 0 | 3 | 3 | 2 | 2 | 56 | Pre-Execution & Procurement | 7 | Design | Main Panel A |  | 65000 | Missing tests | 4 | 2340 | 260 | 1.3332 | 0.26664 | 179.982 | Quality | Engineering | Medium | Pre-Execution & Procurement | Main Panel A | Missing tests |  | 2779.982
Project MODEL 14 - IRIDIUM | Skid | 1 | 0 | 10 | 2 | 2 | 2025 | 14 | 19 | 5 | 4 | 4 | LEVEL 1 | 0 | 3 | 3 | 2 | 2 | 56 | Pre-Execution & Procurement | 8 | Change Requests | Structure |  | 35000 | Documentation error | 3 | 945 | 105 | 0.9999 | 0.19998 | 134.9865 | Cost | Project Management | Low | Pre-Execution & Procurement | Structure | Documentation error |  | 1184.9865
Project MODEL 14 - IRIDIUM | Skid | 1 | 0 | 10 | 2 | 2 | 2025 | 14 | 19 | 5 | 4 | 4 | LEVEL 1 | 0 | 3 | 3 | 2 | 2 | 56 | Pre-Execution & Procurement | 12 | Design | UPS |  | 54000 | No validation | 5 | 2430 | 270 | 1.6665 | 0.3333 | 224.9775 | Quality | Engineering | Low | Pre-Execution & Procurement | UPS | No validation |  | 2924.9775
Project MODEL 14 - IRIDIUM | Skid | 1 | 0 | 10 | 2 | 2 | 2025 | 14 | 19 | 5 | 4 | 4 | LEVEL 1 | 0 | 3 | 3 | 2 | 2 | 56 | Pre-Execution & Procurement | 14 | Submittal package | Floor |  | 4500 | No validation | 5 | 202.5 | 22.5 | 1.6665 | 0.3333 | 224.9775 | Quality | Engineering | Low | Pre-Execution & Procurement | Floor | No validation |  | 449.9775
Project MODEL 14 - IRIDIUM | Skid | 1 | 0 | 10 | 2 | 2 | 2025 | 14 | 19 | 5 | 4 | 4 | LEVEL 1 | 0 | 3 | 3 | 2 | 2 | 56 | Execution | 15 | Design | Switchboard |  | 78500 | Torque error | 3 | 2119.5 | 235.5 | 0.9999 | 0.19998 | 134.9865 | Cost | Production | High | Execution | Switchboard | Torque error |  | 2489.9865
Project MODEL 14 - IRIDIUM | Skid | 1 | 0 | 10 | 2 | 2 | 2025 | 14 | 19 | 5 | 4 | 4 | LEVEL 1 | 0 | 3 | 3 | 2 | 2 | 56 | Execution | 15 | Change Requests | Structure |  | 35000 | Design change | 7 | 2205 | 245 | 2.3331 | 0.46662 | 314.9685 | Cost | Project Management | Low | Execution | Structure | Design change |  | 2764.9685
Project MODEL 14 - IRIDIUM | Skid | 1 | 0 | 10 | 2 | 2 | 2025 | 14 | 19 | 5 | 4 | 4 | LEVEL 1 | 0 | 3 | 3 | 2 | 2 | 56 | Execution | 15 | Design | Structure |  | 35000 | Needs rework | 11 | 3465 | 385 | 3.6663 | 0.73326 | 494.9505 | Schedule | Production | Low | Execution | Structure | Needs rework |  | 4344.9505
Project MODEL 14 - IRIDIUM | Skid | 1 | 0 | 10 | 2 | 2 | 2025 | 14 | 19 | 5 | 4 | 4 | LEVEL 1 | 0 | 3 | 3 | 2 | 2 | 56 | Execution | 16 | Change Requests | Battery VRLA |  |  | Late delivery | 6 | 0 | 0 | 1.9998 | 0.39996 | 269.973 | Schedule | Project Management | Low | Execution | Battery VRLA | Late delivery |  | 269.973
Project MODEL 14 - IRIDIUM | Skid | 1 | 0 | 10 | 2 | 2 | 2025 | 14 | 19 | 5 | 4 | 4 | LEVEL 1 | 0 | 3 | 3 | 2 | 2 | 56 | Execution | 17 | Drawings | Switchboard |  | 78500 | Lack coordination | 5 | 3532.5 | 392.5 | 1.6665 | 0.3333 | 224.9775 | Schedule | Production | Medium | Execution | Switchboard | Lack coordination |  | 4149.9775
Project MODEL 14 - IRIDIUM | Skid | 1 | 0 | 10 | 2 | 2 | 2025 | 14 | 19 | 5 | 4 | 4 | LEVEL 1 | 0 | 3 | 3 | 2 | 2 | 56 | Execution | 18 | Resources | Supplier need |  |  | Schedule delay | 9 | 0 | 0 | 2.9997 | 0.59994 | 404.9595 | Schedule | Project Management | Low | Execution | Supplier need | Schedule delay |  | 404.9595
Project MODEL 14 - IRIDIUM | Skid | 1 | 0 | 10 | 2 | 2 | 2025 | 14 | 19 | 5 | 4 | 4 | LEVEL 1 | 0 | 3 | 3 | 2 | 2 | 56 | Execution | 18 | Change Requests | Switchboard |  | 78500 | Torque error | 3 | 2119.5 | 235.5 | 0.9999 | 0.19998 | 134.9865 | Quality | Engineering | High | Execution | Switchboard | Torque error |  | 2489.9865
Project MODEL 14 - IRIDIUM | Skid | 1 | 0 | 10 | 2 | 2 | 2025 | 14 | 19 | 5 | 4 | 4 | LEVEL 1 | 0 | 3 | 3 | 2 | 2 | 56 | Execution | 18 | Manufacturing | Cable tray structs |  | 23000 | Assembly error | 7 | 1449 | 161 | 2.3331 | 0.46662 | 314.9685 | Quality | Production | Low | Execution | Cable tray structs | Assembly error |  | 1924.9685
Project MODEL 14 - IRIDIUM | Skid | 1 | 0 | 10 | 2 | 2 | 2025 | 14 | 19 | 5 | 4 | 4 | LEVEL 1 | 0 | 3 | 3 | 2 | 2 | 56 | Execution | 18 | Drawings | Cable tray structs |  | 23000 | Alignment error | 5 | 1035 | 115 | 1.6665 | 0.3333 | 224.9775 | Cost | Production | Low | Execution | Cable tray structs | Alignment error |  | 1374.9775
Project MODEL 14 - IRIDIUM | Skid | 1 | 0 | 10 | 2 | 2 | 2025 | 14 | 19 | 5 | 4 | 4 | LEVEL 1 | 0 | 3 | 3 | 2 | 2 | 56 | Execution | 19 | Change Requests | Switchboard |  | 78500 | Torque error | 3 | 2119.5 | 235.5 | 0.9999 | 0.19998 | 134.9865 | Cost | Project Management | Low | Execution | Switchboard | Torque error |  | 2489.9865
Project MODEL 14 - IRIDIUM | Skid | 1 | 0 | 10 | 2 | 2 | 2025 | 14 | 19 | 5 | 4 | 4 | LEVEL 1 | 0 | 3 | 3 | 2 | 2 | 56 | Execution | 20 | Resources | Cooling CRAH |  | 76500 | Missing tests | 4 | 2754 | 306 | 1.3332 | 0.26664 | 179.982 | Quality | Project Management | Medium | Execution | Cooling CRAH | Missing tests |  | 3239.982
Project MODEL 14 - IRIDIUM | Skid | 1 | 0 | 10 | 2 | 2 | 2025 | 14 | 19 | 5 | 4 | 4 | LEVEL 1 | 0 | 3 | 3 | 2 | 2 | 56 | Execution | 25 | Quality | Switchboard |  | 78500 | Missing tests | 4 | 2826 | 314 | 1.3332 | 0.26664 | 179.982 | Quality | Production | Medium | Execution | Switchboard | Missing tests |  | 3319.982
Project MODEL 14 - IRIDIUM | Skid | 1 | 0 | 10 | 2 | 2 | 2025 | 14 | 19 | 5 | 4 | 4 | LEVEL 1 | 0 | 3 | 3 | 2 | 2 | 56 | Execution | 28 | Change Requests | Labels |  | 4500 | Late delivery | 6 | 243 | 27 | 1.9998 | 0.39996 | 269.973 | Schedule | Project Management | Low | Execution | Labels | Late delivery |  | 539.973
[28 empty] | 0 | 0
0

## INFO - Matrix - Data Cells Info
Project MODEL 1 - ALP | Power Module (PM) | 1 | 1 | 6 | 1 | 1 | 2021 | 8 | 8 | 1 | 1 | 1 | EOLT | 0 | 1 | 1 | 1 | 1 | Total Project Duration | Execution Phase | Execution Phase | Categorization | Affection | Vendor | 1000 | Root cause 1 | Estimated Cost Impact (%) | Estimated Cost Impact | Assembly impact (days) | Assembly impact (weeks) | Deviation | Lesson Learnt (≤ 10Words) | Risk description (≤ 10Words) | Best Practices | Project Impact | Department Affection | Especialist | Customer Affection
Project MODEL 2 - NDK3 | Data Center (DC) | 2 | 0 | 10 | 2 | 2 | 2022 | 9 | 9 | 2 | 2 | 2 | FOK | 1 | 2 | 2 | 2 | 2 |  | Pre-Execution & Procurement | 1 | Bill of Material | Battery Cabinet/Rack |  | 1500 | Adverse weather | 5 |  | 1.6665 |  |  |  | Authomatic Description |  | Schedule | Tendering | Electrical | Low
Project MODEL 3 - NND4 | All-in-1 | 3 |  | 14 | 3 | 3 | 2023 | 10 | 10 | 3 | 3 | 3 | FAT | 2 | 3 | 3 | 3 | 3 |  | Execution | 2 | Change Requests | Battery LiThium |  | 2000 | Alignment error | 5 |  | 1.6665 |  |  |  | Authomatic Description |  | Cost | Quality | Mechanical | Medium
Project MODEL 4 - COMPASS PH1 | Skid | 4 |  | 18 | 4 | 4 | 2024 | 11 | 11 | 4 | 4 | 4 | LEVEL 1 | 3 | [5 empty] | Quality Inspection | 3 | Commissioning & Testing | Battery VRLA |  | 2500 | Assembly error | 7 |  | 2.3331 |  |  |  | Authomatic Description |  | Quality | Commissioning | Structure | High
Project MODEL 5 - COMPASS PH2 |  | 5 |  | 20 | 5 | 5 | 2025 | 12 | 12 | 5 | 5 | 5 | LEVEL 2 | 4 | [5 empty] | Energization | 4 | Communication | Busbar |  | 3000 | Client rejection | 10 |  | 3.333 |  |  |  | Authomatic Description |  | Scope | Engineering | Management
Project MODEL 6 - COMPASS PH3 |  | 6 |  |  | 6 | 6 | 2026 | 13 | 13 |  |  |  | LEVEL 3 | [6 empty] | Commissioning | 5 | Contract | Cable grand |  | 3500 | Communication failure | 7 |  | 2.3331 |  |  |  | Authomatic Description |  | Sales | Project Management | Fire
Project MODEL 7 - DLR |  | 7 |  |  | 7 | 7 | 2027 | 14 | 14 |  |  |  | LEVEL 4 | [6 empty] | Diassembly | 6 | Customer & Site | Cable tray structs |  | 4000 | Configuration error | 6 |  | 1.9998 |  |  |  | Authomatic Description |  |  | Warehouse | Monitoring
Project MODEL 8 - NNI1 |  | 8 |  |  | 8 | 8 | 2028 | 15 | 15 | [10 empty] | Logistics paperwork | 7 | Design | Cable Tray capacity |  | 4500 | Connection error | 6 |  | 1.9998 |  |  |  | Authomatic Description |  |  | Production | Quality
Project MODEL 9 - NND2 |  | 9 |  |  | 9 | 9 | 2029 | 16 | 16 | [10 empty] | Packiging | 8 | Drawings | Cable tray type |  | 5000 | Connectivity failure | 7 |  | 2.3331 |  |  |  | Authomatic Description
Project MODEL 10 - COMPASS PH4 |  | 10 |  |  | 10 | 10 | 2030 | 17 | 17 | [10 empty] | Shipping | 9 | KOM Client | Cable type |  | 5500 | Design change | 7 |  | 2.3331 |  |  |  | Authomatic Description
Project MODEL 11 - ELI LILLY 2 |  | 11 |  |  | 11 | 11 | 2031 | 18 | 18 | [10 empty] | Transport Duration | 10 | KOM Factory | Cooling CRAH |  | 6000 | Documentation error | 3 |  | 0.9999 |  |  |  | Authomatic Description
Project MODEL 12 - NND6 |  | 12 |  |  | 12 | 12 | 2032 | 19 | 19 | [10 empty] | Delivery on site | 11 | Manufacturing | Cooling Inrow |  | 6500 | External interference | 4 |  | 1.3332 |  |  |  | Authomatic Description
Project MODEL 13 - NND5 |  | 13 |  |  | 13 | 13 | 2033 | 20 | 20 | [11 empty] | 12 | Price | Customer needs |  | 8000 | Factory defect | 10 |  | 3.333 |  |  |  | Authomatic Description
Project MODEL 14 - IRIDIUM |  | 14 |  |  | 14 | 14 | 2034 | 21 | 21 | [11 empty] | 13 | Project Cost | Customer specifications |  | 9500 | Firmware error | 6 |  | 1.9998 |  |  |  | Authomatic Description
Project MODEL 15 - |  | 15 |  |  | 15 | 15 | 2035 | 22 | 22 | [11 empty] | 14 | Purchashing | Doors |  | 11000 | Firmware failure | 5 |  | 1.6665 |  |  |  | Authomatic Description
Project MODEL 16 - |  | 16 |  |  | 16 | 16 | 2036 | 23 | [12 empty] | 15 | Quality | EHS |  | 12500 | Ground failure | 4 |  | 1.3332 |  |  |  | Authomatic Description
Project MODEL 17 - |  | 17 |  |  | 17 | 17 | 2037 | 24 | [12 empty] | 16 | Resources | Enclosure |  | 14000 | Incompatible item | 7 |  | 2.3331 |  |  |  | Authomatic Description
Project MODEL 18 - |  | 18 |  |  | 18 | 18 | 2038 | 25 | [12 empty] | 17 | Risk | External Pannels |  | 15500 | Incorrect installation | 12 |  | 3.9996 |  |  |  | Authomatic Description
|  | 19 |  |  | 19 | 19 | 2039 | 26 | [12 empty] | 18 | Safety | Floor Termination |  | 17000 | Incorrect wiring | 9 |  | 2.9997 |  |  |  | Authomatic Description
|  | 20 |  |  | 20 | 20 | 2040 | 27 | [12 empty] | 19 | Seismic Level | Labels |  | 18500 | Inexperienced staff | 5 |  | 1.6665 |  |  |  | Authomatic Description
|  | 21 |  |  | 21 | 21 | 2041 | 28 | [12 empty] | 20 | Submittal package | Low voltage |  | 20000 | Insulation failure | 6 |  | 1.9998 |  |  |  | Authomatic Description
|  | 22 |  |  | 22 | 22 | [14 empty] | 21 | Technical Scope | Main Panel A |  | 21500 | Interface failure | 5 |  | 1.6665 |  |  |  | Authomatic Description
|  | 23 |  |  | 23 | 23 | [14 empty] | 22 | Transport/Logistics | Main Panel B |  | 23000 | Inventory error | 3 |  | 0.9999 |  |  |  | Authomatic Description
|  | 24 |  |  | 24 | 24 | [14 empty] | 23 |  | Medium voltage |  | 24500 | Labeling error | 3 |  | 0.9999 |  |  |  | Authomatic Description
|  | 25 |  |  | 25 | 25 | [14 empty] | 24 |  | Monitoring Panel |  | 26000 | Labeling error | 3 |  | 0.9999 |  |  |  | Authomatic Description
|  | 26 |  |  | 26 | 26 | [14 empty] | 25 |  | Netbots |  | 27500 | Lack coordination | 5 |  | 1.6665 |  |  |  | Authomatic Description
|  | 27 |  |  | 27 | 27 | [14 empty] | 26 |  | Overhead Cooling |  | 29000 | Language error | 3 |  | 0.9999 |  |  |  | Authomatic Description
|  | 28 |  |  | 28 | 28 | [14 empty] | 27 |  | Panelling |  | 30500 | Language error | 3 |  | 0.9999 |  |  |  | Authomatic Description
|  | 29 |  |  | 29 | 29 | [14 empty] | 28 |  | PDU |  | 32000 | Late delivery | 6 |  | 1.9998 |  |  |  | Authomatic Description
|  | 30 |  |  | 30 | 30 | [14 empty] | 29 |  | Requiring site works |  | 33500 | Measurement error | 4 |  | 1.3332 |  |  |  | Authomatic Description
[5 empty] | 31 | 31 | [14 empty] | 30 |  | Service Panel |  | 35000 | Missing cleaning | 2 |  | 0.6666 |  |  |  | Authomatic Description
[5 empty] | 32 | 32 | [14 empty] | 31 |  | Signage Safety |  | 36500 | Missing kit | 5 |  | 1.6665 |  |  |  | Authomatic Description
[5 empty] | 33 | 33 | [14 empty] | 32 |  | Site Energized |  | 38000 | Missing signage | 2 |  | 0.6666 |  |  |  | Authomatic Description
[5 empty] | 34 | 34 | [14 empty] | 33 |  | Site Readiness |  | 39500 | Missing support | 4 |  | 1.3332 |  |  |  | Authomatic Description
[5 empty] | 35 | 35 | [14 empty] | 34 |  | Structure |  | 41000 | Missing tests | 4 |  | 1.3332 |  |  |  | Authomatic Description
[5 empty] | 36 | 36 | [14 empty] | 35 |  | Supplier need |  | 42500 | Missing tools | 4 |  | 1.3332 |  |  |  | Authomatic Description
[5 empty] | 37 | 37 | [14 empty] | 36 |  | Supply Chain |  | 44000 | Missing training | 4 |  | 1.3332 |  |  |  | Authomatic Description
[5 empty] | 38 | 38 | [14 empty] | 37 |  | Switchboard |  | 45500 | Needs rework | 11 |  | 3.6663 |  |  |  | Authomatic Description
[5 empty] | 39 | 39 | [14 empty] | 38 |  | UPS |  | 47000 | Network failure | 6 |  | 1.9998 |  |  |  | Authomatic Description
[6 empty] | 40 | [14 empty] | 39 |  | Vertical support |  | 47500 | No access | 3 |  | 0.9999 |  |  |  | Authomatic Description
[6 empty] | 41 | [14 empty] | 40 |  | Weather conditions |  | 48000 | No access | 3 |  | 0.9999 |  |  |  | Authomatic Description
[6 empty] | 42 | [14 empty] | 41 |  | Z - Other |  | 48500 | No backup | 3 |  | 0.9999 |  |  |  | Authomatic Description
[6 empty] | 43 | [14 empty] | 42 |  |  |  | 49000 | No calibration | 4 |  | 1.3332 |  |  |  | Authomatic Description
[6 empty] | 44 | [14 empty] | 43 |  |  |  | 49500 | No connectors | 3 |  | 0.9999 |  |  |  | Authomatic Description
[6 empty] | 45 | [14 empty] | 44 |  |  |  | 50000 | No labeling | 2 |  | 0.6666 |  |  |  | Authomatic Description
[6 empty] | 46 | [14 empty] | 45 |  |  |  | 50500 | No manual | 2 |  | 0.6666 |  |  |  | Authomatic Description
[6 empty] | 47 | [14 empty] | 46 |  |  |  | 51000 | No power | 6 |  | 1.9998 |  |  |  | Authomatic Description
[6 empty] | 48 | [14 empty] | 47 |  |  |  | 51500 | No signal | 3 |  | 0.9999 |  |  |  | Authomatic Description
[6 empty] | 49 | [14 empty] | 48 |  |  |  | 52000 | No signal | 4 |  | 1.3332 |  |  |  | Authomatic Description
[6 empty] | 50 | [14 empty] | 49 |  |  |  | 52500 | No spares | 3 |  | 0.9999 |  |  |  | Authomatic Description
[6 empty] | 51 | [14 empty] | 50 |  |  |  | 53000 | No supervision | 6 |  | 1.9998 |  |  |  | Authomatic Description
[6 empty] | 52 | [18 empty] | 53500 | No validation | 5 |  | 1.6665 |  |  |  | Authomatic Description
[25 empty] | 54000 | Packing error | 3 |  | 0.9999 |  |  |  | Authomatic Description
[25 empty] | 54500 | Permission error | 3 |  | 0.9999 |  |  |  | Authomatic Description
[25 empty] | 55000 | Planning error | 6 |  | 1.9998 |  |  |  | Authomatic Description
[25 empty] | 55500 | Pressure failure | 5 |  | 1.6665 |  |  |  | Authomatic Description
[25 empty] | 56000 | Protocol error | 4 |  | 1.3332 |  |  |  | Authomatic Description
[25 empty] | 56500 | Route error | 4 |  | 1.3332 |  |  |  | Authomatic Description
[25 empty] | 57000 | Safety error | 6 |  | 1.9998 |  |  |  | Authomatic Description
[25 empty] | 57500 | Schedule delay | 9 |  | 2.9997 |  |  |  | Authomatic Description
[25 empty] | 58000 | Sensor error | 4 |  | 1.3332 |  |  |  | Authomatic Description
[25 empty] | 58500 | Sensor failure | 5 |  | 1.6665 |  |  |  | Authomatic Description
[25 empty] | 59000 | Sequence error | 4 |  | 1.3332 |  |  |  | Authomatic Description
[25 empty] | 59500 | Software error | 8 |  | 2.6664 |  |  |  | Authomatic Description
[25 empty] | 60000 | System failure | 6 |  | 1.9998 |  |  |  | Authomatic Description
[25 empty] | 60500 | Torque error | 3 |  | 0.9999 |  |  |  | Authomatic Description
[25 empty] | 61000 | Transport damage | 8 |  | 2.6664 |  |  |  | Authomatic Description
[25 empty] | 61500 | Voltage error | 5 |  | 1.6665 |  |  |  | Authomatic Description
[25 empty] | 62000 | Wrong documentation | 3 |  | 0.9999 |  |  |  | Authomatic Description
[25 empty] | 62500 | Wrong drawings | 4 |  | 1.3332 |  |  |  | Authomatic Description
[25 empty] | 63000 | Wrong material | 6 |  | 1.9998 |  |  |  | Authomatic Description
[25 empty] | 63500 | Z-Other | 5 |  | 1.6665
64000
64500
65000
65500
66000
66500
67000
67500
68000
68500
69000
69500
70000
70500
71000
71500
72000
72500
73000
73500
74000
74500
75000
75500
76000
76500
77000
77500
78000
78500
79000
79500
80000
80500
81000
81500
82000
82500
83000
83500
84000
84500
85000
85500
86000
86500
87000
87500
88000
88500
89000
89500
90000
90500
91000
91500
92000
92500
93000
93500
94000
94500
95000
95500
96000
96500
97000
97500
98000
98500
99000
99500
100000
100500
101000
101500
102000
102500
103000
103500
104000
104500
105000
105500
106000
106500
107000
107500
108000
108500
109000
109500
110000
110500
111000
111500
112000
112500
113000
113500
114000
114500
115000
115500
116000
116500
117000
117500
118000
118500
119000
119500
120000
120500
121000
121500
122000
122500
123000
123500
124000
124500
125000
125500
126000
126500
127000
127500
128000
128500
129000
129500
130000
130500
131000
131500
132000
132500
133000
133500
134000
134500
135000
135500
136000
136500
137000
137500
138000
138500
139000
139500
140000
140500
141000
141500
142000
142500
143000
143500
144000
144500
145000
145500
146000
146500
147000
147500
148000
148500
149000
149500
150000
150500
151000
151500
152000
152500
153000
153500
154000
154500
155000
155500
156000
156500
157000
157500
158000
158500
159000
159500
160000
160500
161000
161500
162000
162500
163000
163500
164000
164500
165000
165500
166000
166500
167000
167500
168000
168500
169000
169500
170000
170500
171000
171500
172000

## Project Model Info
Project MODEL
Project MODEL 1 - ALP
Project MODEL 2 - NDK3
Project MODEL 3 - NND4
Project MODEL 4 - COMPASS PH1
Project MODEL 5 - COMPASS PH2
Project MODEL 6 - COMPASS PH3
Project MODEL 7 - DLR
Project MODEL 8 - NNI1
Project MODEL 9 - NND2
Project MODEL 10 - COMPASS PH4
Project MODEL 11 - ELI LILLY 2
Project MODEL 12 - NND6
Project MODEL 13 - NND5
Project MODEL 14 - IRIDIUM
Project MODEL 15 -
Project MODEL 16 -
Project MODEL 17 -
Project MODEL 18 -